ITB  DOCUMENT FOR THE PROJECT MANAGEMENT CONSULTANCY SERVICES (ENGINEERING PROCUREMENT AND CONSTRUCTION MANAGEMENT)  FOR THE PROJECT

“NAPTHA HYDROTREATING UNIT AND CONTINUOUS   CATALYTIC    REGENERATION   REFORMER UNIT  AT BPCL,MUMBAI REFINERY”

| SR. NO. | CONTENTS | PAGE NO. |
| --- | --- | --- |
| 1 | (a) INSTRUCTION TO BIDDERS (b) QUALIFICATION CRITERION | 2-4 |
| 2 | SECTION –I : (a)INTRODUCTION & PROJECT SCOPE (b)PROCESS DESCRIPTION ANNEXURE-1 (c)UTILITY STUDY ANNEXURE-2 | 5-8 9-11 12-17 |
| 3 | SECTION-II : SCOPE OF WORK,DOCUMENT CONTROL, HSE & QUALITY CONTROL GUIDELINES | 18-67 |
| 4 | SECTION – III : PROJECT IMPLEMENTATION PHILOSOPHY | 68-69 |
| 5 | SECTION-IV : REMUNERATION, CONTRACT PRICE AND PAYMENT TERMS [ BIDDER TO FILL PRICE]. | 70-76 |
| 6 | SECTION- V : TIME SCHEDULE [ BIDDER TO FURNISH THE SCHEDULE OF PROJECT ] | 77 |
| 7 | SECTION-VI : WARRANTIES & GUARANTEES | 78-80 |
| 8 | SECTION-VII : OWNERS OBLIGATIONS | 81-83 |
| 9 | SECTION-VIII : BIDDERS ORGANOGRAM [ BIDDER TO FURNISH] | 84 |
| 10 | Commercial Terms and Conditions | 85-88 |
| 11 | Memorandum of agreement |  |
| 12 | FORM - A |  |
| 13 | General Terms and Conditions |  |
| 14 | Special Safety Conditions |  |
| 15 | Financial Deterrent for violation of HSC |  |
| 16 | Format for EMD |  |
| 17 | Regret Proforma |  |
| 18 | Integrity Pact |  |

INSTRUCTION TO BIDDERS

BPCL is in the process of installing continuous Catalytic Regeneration Reformer Unit licensed by M/s Axens IFP Group Technologies, France, in Mumbai refinery for which Project Management Consultancy works are being tendered out on press notification basis.

BPCL invites sealed bids for Project Management Consultancy ( Engineering Procurement and Construction Management ) under single stage  two envelop system (Part I :  Techno commercial part and  Part II : Price part) from competent agencies from India and abroad with sound technical and commercial capabilities  fulfilling the Qualification Criteria stated as below :

The tender scope broadly consists of :

| 1) | Checking process design given by process licensor |
| --- | --- |
| 2) | Carry out Process Residual Engineering |
| 3) | Carry out Complete Detailed Engineering including HAZOP. |
| 4) | Complete tendering and procurement services including expediting services except for overseas orders |
| 5) | Carry out inspection activities of all ordered materials |
| 6) | Carryout Inspection services for all construction activities including construction bought out items. |
| 7) | Carry out all construction activities at site including inspection activities |
| 8) | Pre commissioning assistance and commissioning assistances. |
| 9) | Complete documentation from Contract Agreement to detail operation Manual i.e. Design basis, Purchase and tendering procedure, PFD, P&IDs, Hazop, Safety Procedure, Contract execution procedure, documentation pertaining to all executed work , as built drawings, start –up, shut down ,emergency handling and procedure for handling equipments / utilities failure etc. |
| 10) | Adequacy study for utilities including flare and instrument/process air system. |

The details  of jobs to be executed  are given in attached Scope of work.

Qualification Criteria :

Agencies intending to participate shall fulfill following qualification criteria (technical and financial) described below :

Experience Criteria :

Bidder who seeks qualification should have completed in the immediate  seven years  to be reckoned from the date of bid submission at-least one similar   work of  project value not less than Rs. 500 crores or two  similar  works of project value not less than Rs.300 crores.

The bidder shall also have provided  Project Management Consultancy services  including complete detailed Engineering, residual engineering, procurement servicing including tendering, inspection and expediting ,construction supervision at site including site inspection, pre-commissioning and complete project management for at-least one CCR plant in Refinery  in  India/ abroad.

The party should posses  technical resources to execute this job as follows:

The technical resources should comprise of at-least 10 years minimum experience in Projects Engineering in the following categories.

- Project Management

- Process inclusive  of residual engineering

- Equipment and piping Design.

- Heat and mass Transfer.

- Construction

- Instrumentation.

- Civil

- Electrical

- Costing

- Inspection and corrosion.

All other supporting  staffs to execute the project.

Financial Criteria:

Annual Turnover:

The Annual turn over of the bidder shall not be lower than Rs.150 crores  in the preceding three financial years

Net-worth:

Net-worth of the bidder during Financial Year 2007-2008 shall be positive.

Bidder should not be under liquidation, court receivership or similar proceedings. Bidder shall furnish documentary evidence by way of copies of work orders, completion certificates and balance sheets including Profit and Loss Accounts, Certificates from bank etc. along with the Bid to   establish Bidder’s conformance to Qualification Criteria.

Failure to meet the above Qualification Criteria will render the Bid to be rejected. Therefore, the bidder shall in his own interest furnish complete documentary evidence in the first instance itself, in support of their fulfilling the Qualification Criteria as given above.

Bids on Consortium or Joint venture basis are not acceptable.

SECTION – I

# CONTINUOUS CATALYTIC REGENERATION REFORMER UNIT  (CCR)  PROJECT AT BPCL,MUMBAI REFINERY

1.0	INTRODUCTION:

Bharat Petroleum Corporation Ltd intends to set up a new Continuous Catalytic Regeneration Reformer Unit (CCR) of 0.9 MMTPA capacity with 30% design margin and matching Naphtha Hydro Treatment unit (NHT) including Pressure Swing Adsorber (PSA) unit in Mumbai Refinery.

For  NHT, three feed case, and for CCR/PSA two feed case would be considered for development of PFD / P&ID and equipments would be designed based on dictating case.

Process package for NHT/CCR will be available to CONSULTANT by September 2009.

The CCR Project is scheduled to be  mechanically  completed by 26 months from handing over of critical equipment data sheets.

Bharat Petroleum Corporation Ltd. (R) is planning to appoint a Project  Management Consultant who will closely interact with BPCL & process Licensor  M/s Axens and M/s LINDE for PSA to provide PMC services as per Scope of Work in this tender document. The project execution methodology shall be Conventional.

## 1.1        TECHNOLOGY SELECTION & BASIC ENGINEERING

The process of selection of technology has been  completed and technology from M/s Axens / M/s Linde for PSA  has been selected for this project.. Further, we are in the process of obtaining basic design  Engineering package (BDEP) from the process licensor.

PMC FOR CCR PROJECT.

The major facilities planned to meet the objective of CCR Project, are categorised in to following sections. CONSULTANTs scope includes

adequacy checks and system modifications for the facilities/portion of work affected as a result of new units.

Based on  the BDEP supplied by the licensor ,Consultant has to carry out the detail engineering for NHT/CCR and PSA units.

Besides above, if during detailed engineering, any other equipment/ piping/ facility found limiting, engineering for the same shall be part of PMC scope.

A BDEP is being prepared for the project by the process licensor M/s Axens / Linde. Bidders are required to enter into a confidentially agreement with the Process licensor (M/s Axens).

2.0	PROJECT SCOPE:

# Background:

Implementation of Refinery Modernization Project (RMP) and Catalytic Reformer Unit Revamp (CRU) at BPCL (MR) enabled production of MS and HSD meeting BS-II & Euro 3 specifications.  In order to upgrade MS and HSD fuels meeting Euro 3 / Euro 4 equivalent norms by 2010, additional processing facilities and revamp of existing treatment facilities would be necessary accordingly suitable actions were initiated and modification jobs are in progress.   Current production and post April 2010 production of MS and HSD in Metros and rest of the country are given below:

| MMTPA |
| --- |
| Crude Mix considered, LS / HS | 6 / 6 |
|  | Current production | Production post April 2010 |
|  | MS | HSD | MS | HSD* |
| BS-2 | 0.6 | 3.4 | 0.7 | 3.4 |
| Euro-3 | 0.5 | 0.7 | 0.5 | 0.7 |
| Total | 1.1 | 4.1 | 1.2 | 4.1 |

* With export of about 0.2 MMTPA of High sulphur Diesel.

# Facilities to meet part of Euro 3 / Euro 4 qualities MS/HSD:

Short term low cost modifications jobs are in progress in BPCL (MR) to supply limited Euro 4 quality MS and HSD from 2010. The facilities considered to produce Euro 4 quality MS and HSD are as follows:

- Revamp of existing Diesel Hydrodesulphurization unit (DHDS) to 6000 MT/D from existing 4200 MT/D.

- Set up of Fluidized Catalytic Cracking gasoline (FCC gasoline) splitter facilities.

- Sourcing Reformat of 200 TMTPA from Kochi as part of Crude Expansion Modernization Project – II (CEMP-II). This provision has already been made in the new Continuous Catalytic Reformer Unit (CCR) which is being set up at Kochi Refinery to meet Mumbai Refinery requirement.

Aforementioned modifications / facilities are in progress as per schedule.

Implementation of above process facilities / activities and availability of 200 TMT/A of Reformat to Mumbai Refinery from Jan 2010 would enable production of MS  & HSD in BPCL (MR) as detailed above.

# Proposal for MS Up-gradation

Auto fuel policy stipulates supply of Euro 4 & Euro 3 Auto Fuels for 13 major cities and rest of the country respectively from April 2010. Auto Fuel policy is under review by Government and based on interactions with the Review committee, it is expected that their recommendations would be in line with original recommendations of Euro 4 for major cities & Euro 3 for rest of the country from April 2010. However, Automobile manufacturers are demanding implementation of Euro 4 for entire country simultaneously. Further, due to pressures from Automobile manufacturers and environmentalists, Euro 4 or possibly Euro 5 (Sulphur <10 ppm) specifications are likely to be specified sooner than later.

In view of the above, preliminary in-house configuration studies using Linear Program (LP) models have been carried out and identified Continuous Catalytic Regenerator Reformer (CCR) is required. The CCR would provide a launching pad for up-gradation of Auto Fuels to Euro 4 & Euro 5 by providing incremental Hydrogen for Hydro-treatment facilities needed for HSD up-gradation to qualities of Euro 4 / Euro 5.

# Project Description

It is proposed to install Continuous Catalytic Regenerator Reformer (CCR) of 0.9 MMTPA capacities with 30% design margin with matching new Naphtha Hydro treatment unit (NHT) and Pressure Swing Adsorber (PSA) for Hydrogen recovery ex CCR. The CCR project includes NHT, CCR and PSA. Licensors selected for CCR project is M/s Axens. Description of process is given (Refer Annexure 1)

# Utilities and Offsite

Feasibility of utilities and offsite facilities considering adequacy of existing system need to be established by detailing engineering group. Routing of feed and products has to be developed by PMC. PFD, P&ID, equipment and instrument datasheet have to be developed from existing unit hook up point to NHT battery limit and all rundown product streams from NHT/CCR/PSA to desired destination (Refer Annexure 2). HAZOP has to be carried out for up to tie –in point & ISBL.

# Plot Plan

It is proposed to set up CCR facilities in the plot currently occupied by Aromatic tanks (tanks 360,361,362,363,364,365,366 and P/H-11) and in redundant IBP-60 spheres(S-354,S-355).These two plots are separated by a common road. Already dismantling work of tanks is in progress. Vacant area would be made available for detailed engineering group for set up of CCR project. Site would be available for construction from November 2009

# Project Schedule

It is expected that CCR project would be implemented within time period of 26 months from the date of  from handing over of critical equipment data sheets.

Annexure 1

Process Description

Process description of facilities such as, (1) Set up of CCR with matching NHT & PSA associated facilities, and (2) Matching offsite / utilities are given below.

(1) Naphtha Hydro treatment Unit (NHT)

The purpose of NHT unit is to eliminate the impurities, mainly Sulphur and Nitrogen, which would affect the performance of downstream Reformer catalyst.

NHT includes two main section namely (a) Reaction section and (b) Stripping section.

Mixture of naphtha (Straight run Naphtha from existing Reformer Feed Unit / Crude Unit) and Cracked Gasoline heart cut naphtha from new Gasoline splitter are stored in surge drum. This naphtha mixture is pumped to the reaction pressure and mixed with hydrogen recycle / hydrogen make-up gas.

Reaction section:

Reaction section shall comprise of equipments such as feed pump, feed / effluent exchangers, charge heater, reactor, effluent condenser/coolers, separator and Knock out drums. Recycle & make-up gas compressor is required.

Stripping section:

The feed / bottom exchanger, stripper column, Re-boiler, overhead condenser and other associated facilities are provided in Stripping section.

The bottom product, Desulfurized Stabilized Naphtha (DSN) after heat exchange with stripper feed is sent to the Continuous Catalytic Reformer Unit.

(2)         Continuous Catalytic Regeneration Reformer unit (CCR)

Hydro-treated naphtha from new NHT with matching capacity of CCR is combined with recycle gas and heated to reaction temperature in the charge heater before processing it in reactors.  Reforming reaction that take place in the reactor are predominantly endothermic, hence inter-reactor heaters are employed to maintain a constant inlet temperature profile for the individual reactors.

Configuration of four reactors is used to process DSN to B & T rich reformat and heavy reformat as rich octane blend component for Motor Spirit. Heat from effluent of the last reactor is exchanged with the combined feed, condensed in the product trim cooler and sent to separator.

The total H2-rich gas from the separator is compressed in the recycle gas compressor.  The recycle portion of the gas is returned to the combined feed exchanger and the net portion is sent to the recontact section.  To maximize LPG a cryogenic LPG recovery section is used.  Pressure Swing Adsorber is used to improve Hydrogen purity of hydrogen stream ex CCR.

Reactor effluent is sent to the debutanizer after being preheated in debutanizer feed/bottom exchanger.  Stabilizer Reformate is cooled in feed / bottom exchanger followed by air/trim cooler before being routed to storage.  LPG from debutanizer is cooled in LPG trim cooler and routed to storage.

The regeneration section of the reformer provides a continuous stream of clean coke-free active catalyst that is returned back to the reactors.  Continuous circulation of regenerated catalyst helps maintain optimum catalyst performance at high severity conditions for long on-stream periods of reforming operation.

A Reformate Splitter fractionates the entire Reformate produced in the reformer unit into light, mid and heavy fractions.  The light Reformate withdrawn from the top is routed to the Naphtha pool. Mid cut is routed to Aromatic Recovery Unit and the Bottom heavy Reformate is sent to the Gasoline Pool.   The Splitter has an air cooled condenser and a Reboiler.  The bottom product is cooled in feed bottom exchanger, air cooler and water cooled exchanger.

(3)          Pressure Swing Adsorber unit (PSA)

Standard PSA would be in service to recover maximum Hydrogen from CCR unit and improve Hydrogen purity to desired level.

(4)          Utilities and Process Lines

All utilities and process lines inside the battery limit and from the mother header till the battery limit shall be in the scope of PMC.

The detailed study of existing utilities and adequacy is covered in Annexure 2

(5)      Steam Generation / Consumption within ISBL

PMC is expected to carry out the basic design engineering and all other detailed engineering required for steam generation/consumption within ISBL.

- Control room: Existing RMP control room has to be suitably modified by

detailed engineering contractor to accommodate facilities required for CCR

project else design a new control room

(7)      Switch house : New switch house is envisaged near CCR plot. Detailed

engineering contractor to study and accommodate switch house required

for CCR unit.

Annexure 2

UTILITIES

The Utility requirements for the proposed facilities are detailed below

Scope of PMC  is to study the adequacy of   the existing Refinery system. After the study suggest whether the new requirement for NHT/CCR can be fulfilled by the existing system or new systems have to be provided. If new systems are be provided , then capacity requirement of new system should be specified.

The consultant has to provide the draft report and present to BPCL     for comments and  approval. This draft report shall also consist of specification sheet for all the new facilities specified. These data sheets shall form the basis of  all such utility requirements  to be separately executed ,  These specification sheets should also enable BPCL to prepare the estimate for implementation.

The consultant should incorporate all comments from BPCL and submit a final Adequacy report to BPCL   , this report shall  form basis for further engineering/implementation

The cost estimate for all new utilities packages should also be provided in the report.

The study report of utilities have to be completed and submitted to BPCL  within 2 months of date of FOI

N2 Requirement

Design capacities of two Nitrogen units are (1) Old N2 unit (Gas-1350 Nm3/Hr and Liquid–300 Nm3/Hr) and (2) N2 unit-RMP (Gas-780 Nm3/Hr and Liquid–280 Nm3/Hr). The N2 requirement post LOBS is about 807 Nm3/Hr which is met from existing gaseous nitrogen of 780 Nm3/Hr and by vaporizing liquid nitrogen of gas equivalent 280 Nm3/Hr. Liquid N2 storage take care of peak demand (RMP-1275 Nm3/Hr) and start-up, shutdown and restart of RMP units (11000 Nm3/Hr). It is assumed that LOBS unit start up is not simultaneous with HCU and Hydrogen unit of RMP.

Flare system

The flare load of new NHT and CCR shall be given by Process Licensor. Study the existing system and check adequacy of the flare system  taking into consideration the new load. If the existing system is not adequate  study should specify the details of new system .

Power Requirement

The additional power requirement for the proposed facilities is about 15 MW. This additional power requirement is proposed to be sourced from Tata Power Company after suitable augmentation of existing system. It is expected that 22KV feeder would be provided in addition to existing two feeders of 22KV capacity. Detail engineering contractor scope includes provision of all related electrical system from Main Receiving Station of BPCL (MR) to CCR project facilities including switch house. It is envisaged that new switch house for CCR project would be provided near TDU or in the plot area of IBP-60 sphere area. Proper relay coordination study shall be done to take care of reliability of new / existing system.

Fuel Gas/ Naphtha

It is envisaged that clean, environmental friendly natural gas / fuel gas / Naphtha would be used as fuel. Gas produced within CCR unit would be used and additional fuel of about 65 MT/D would be met from existing fuel system in Mumbai Refinery. However based on adequacy check by detailed engineering contractor additional facilities for both fuel gas  and naphtha have to be incorporated.

Condensate

Existing condensate shall be routed back to existing refinery condensate network at boiler house for Pure Condensate and DM Plant for impure condensate. However based on adequacy check by detailed engineering contractor additional facilities have to be incorporated.

Cooling Water

BPCL proposed for the  Raw cooling tower to meet the requirement of CCR cooling water. Existing  Raw water cooling tower  at DHDS/ARU with 3 cells each 3400 m3/Hr capacity. However based on the adequacy check by detailed engineering contractor additional facilities have to be incorporated

Boiler Feed Water

Post LOBS requirement of Boiler Feed Water (BFW) for RMP units is about 135 MT/Hr as against design of 150 MT/Hr. Additional Boiler Feed Water requirements for CCR is about 27 MT/Hr. Existing DM plants have surplus capacity and this additional requirement shall be met from the existing unit. However based on adequacy check by detailed engineering contractor additional facilities have to be incorporated.

Re-circulating Raw Water bearing cooling system

Raw water requirement post LOBS is about 1746 m3/Hr which is already met by impeller replacement in pumps. Based on the increase in raw water requirement due to CCR, HCU revamp etc adequacy check to be carried out by detailed engineering contractor additional facilities have to be incorporated.

Steam System ( Medium / Low Pressure steam)

PMC is expected to develop process for generating steam using waste heat from the process. Surplus steam after consumption within CCR project has to be exported to Refinery header.

)

Instrument/Process Air System

Refinery Compressed air system is operated at three different pressures for meeting requirement of Instrument air and Plant air for Old Units as well as new RMP units. Two compressors of 4500 m3/hr with operating pressure of 8.0 Kg/Cm2 for DHDS and 4.8 Kg/Cm2 for Instrument air to Old units respectively. For RMP units, two compressors of capacity 4500 m3/hr each are in service, with operating pressure of 7.0 kg/Cm2 for Instrument air and 8.0 Kg/Cm2 for Plant Air.    Consultant to study the existing system and check adequacy based on CCR requirement and prepare report.

OFFSITES

Offsite facilities envisaged in CCR project are as follows:

Waste water Treatment plant (MINAS): The waste liquids are withdrawn from the regeneration loop washing drum and sent to the waste water treatment. It is expected that about 120 MT/D of waste water having NaCl, NaOH, Na2CO3, and NaOCl would be routed to MINAS. This waste water would have spent caustic of 6wt% of 3 MT/D.   Existing MINAS unit is capable of handling additional waste water, however based on adequacy check by detailed engineering contractor additional facilities have to be incorporated.

Closed Blow down system: A closed drain system is incorporated with the intent of having a collection and disposal facility for handling the non-congealing hydrocarbon drains in the plant. Closed blow down drum would be placed underground to receive non congealing liquid and transferred to OSBL as slops. This slops in turn routed to existing refinery slops tanks T 121 / 122 / 126. However based on adequacy check by detailed engineering contractor additional facilities have to be incorporated.

Oily waste water sewer (OWS): Alternate draining arrangements are considered for all equipments to open funnels connected to OWS pipeline network routed to underground pit. Using pumps, liquid ex OWS is transferred to refinery slops tanks. However based on adequacy check by detailed engineering contractor additional facilities have to be incorporated.

Acid gas: Route acid gas ex NHT to acid gas flare / normal flare.

Contaminated rain water system (CRWS):   A separate CRWS network consisting of underground lines and manholes is considered  which will be routed to existing CRWS system. However based on adequacy check by detailed engineering contractor additional facilities have to be incorporated.

Flushing Oil System: Requirement of flushing oil if any will be met from existing Refinery system.

Product Tanks: Existing tanks within Refinery would be used for storing product streams ex CCR and hence no additional tanks are expected. However based on adequacy check by detailed engineering contractor additional tanks with blending facilities have to be incorporated.

Process:

Feed:

Routing of F1, MK, HN streams from Crude Distillation Unit (CDU 1) and SCN stream from CDU 2 up to NHT battery limit

Routing of mid cut & heavy cut ex Gasoline splitter column at Catalytic Cracking Unit (CCU) up to NHT battery limit

Routing of Splitter-2 tops and bottoms from Reformer Feed Unit (RFU), Splitter-2 top, Splitter-3 bottom ex New Solvent Unit up to NHT battery limit.

Routing of HN from CDU 3, LN and HN streams from Hydro-cracker (HCU) up-to NHT battery limit

Routing of Hydrogen import (~ 23 Kg/cm2g) to NHT/CCR ex Hydrogen generation unit HGU-1 and HGU-2

Routing of high pressure Hydrogen import (~ 40 Kg/cm2g) to NHT/CCR ex make-up gas compressor of DHDS & HCU

Stream Disposition: All rundown header adequacies to be checked accordingly route hydro-treated naphtha ex NHT to existing storage system, Fuel gas to RMP fuel gas header, LPG to mounded bullet, H2 export to new / existing pipeline network to DHDS & HCU, Light Reformat to Naphtha header & existing New solvent unit, Mid cut to existing Aromatic Recovery Unit & naphtha header, Heavy Reformat to blend header & storage tank at blending section. We envisage a new hydrogen network to existing consumer (DHDS/Hydro-cracker) to be established. Hence based on adequacy check by detailed engineering contractor additional facilities have to be incorporated.

SECTION-II

SCOPE OF WORK, DOCUMENT CONTROL REQUIREMENTS, PROJECT CONTROL REQUIREMENTS, HSE GUIDELINES, PROJECT QUALITY GUIDELINES

A) SCOPE OF WORK

###### CONSULTANT’S  SCOPE OF WORK

Consultant’s  scope of services for the PROJECT shall, in general consist of comprehensive Project Management from  Basic Engineering / design to final completion/ commissioning and guarantee test run including planning/scheduling, project monitoring, cost control, quality assurance, setting Project procedures, interact/co-ordinate and obtaining package for licensed unit with the process licensor,  and other related services to BPCL, for the scope of Project and the Project implementation strategy as described herein.

The scope of services by CONSULTANT is divided under following   phases.

- Project Management.

- Infrastructure / Pre-Project phase

- Basic Engineering.

- Preparation of 3D modelling and review with client/Licensor at 60%  and 90%.

- Project Implementation

6.  Construction Management

7 . Pre-commissioning & Commissioning

1.   PROJECT MANAGEMENT

- Develop project strategy and schedules, establish monitoring system, reporting system, quality control system and project information system.

- Develop overall project execution philosophy and project co-ordination procedures.

- Establish procedures covering mechanical completion, pre-commissioning, commissioning, start-up and performance test run of various units and their taking over from respective agencies.

- Maintain project procedures through regular review / updating / amendment.

- Preparation of an overall project schedule, /network, identifying critical path, milestones, priority activities and target dates for completion.

- Updating the Master Schedule as and when necessary.

- Hold regular project review meeting with OWNER, Contractor and Critical vendors. Co-ordination with Licensor and other vendors/ works contractors.

- Review, approve and monitor detailed schedules of contractors & vendors.

- Establish formal lines of communication with Owner , Vendors, Contractors and Process Licensor .

Cost  Estimation :

- CONSULTANT shall prepare project cost estimate with phasing within 6 months of the start of project.

- Project cost update shall be carried out quarterly and also on completion of major ordering as well as after commissioning. Cost commitments shall be provided in each recommendation as a part of monitoring and cost control shall be in place in all phases of project execution.

- Cost estimation shall be provided in case of single vendor and for all tagged items including special instrument items.

Quality Control :

- Prepare overall Quality Assurance and Quality Control (QA/QC) System for the various phases of the PROJECT (i.e. Engineering, Procurement, Construction and Commissioning).

- Keep regular surveillance  and audit Quality Assurance Program of  contractors and vendors.

- Prepare QA/QC report (this includes NCR / Deviation raised and settled during engineering, procurement & construction phases) for the Project complex on a regular basis identifying areas for action by concerned agencies.

- CONSULTANT shall obtain as-built documentation from respective vendors/ contractors and organise mark-up/preparation of as-built documentation for conventional portion with contractor’s assistance in requisite format and copies before commencement of start-up activities.

- Infrastructure / Pre-Project phase

- Review site(s) meteorological data, earthquake/ seismic survey reports, preliminary soil report and other data as available.  CONSULTANT will identify any additional data as required and initiate actions for obtaining the same.  Such action will include preparation of tender document, recommendation of contractor and supervision of the contractor(s) work.

- Provide an estimate of construction water and construction power requirement at Refinery, including broad specifications of the same.

- Carryout basic engineering, design and execution of complete construction water and construction power distribution schemes    (from the point source at site identified by BPCL within Refinery).

- The Plot plan as supplied by BPCL  will be reviewed,

Updated  and detailed by  CONSULTANT subsequently at

regular   intervals.

- Estimate requirement of Infrastructure/pre-Project/construction   and construction enabling facilities for  the  Project and initiate action for their execution through  contractor(s).

- Above shall include preparation of plans including Specifications Engineering / Material Requisitions / tender enquiries, evaluation of bids, recommendations to BPCL.

- Transportation study of Heavy Equipment/ODC movement during construction phase to identify constraints in movement outside as well as inside refinery premises. Consultant’s scope includes preparation of tender, select party, co-ordination, obtain report and develop facilities to enable smooth transportation of equipment up to construction site.

- Advise BPCL for establishing various technical support facilities   such as communication, computer software, etc. (CONSULTANT has considered establishing internet facility/ connectivity in his office and expects the same to be available with major contractors and matching facilities for BPCL).

- CONSULTANT will develop following in close co-ordination with   BPCL by adopting an appropriate prequalification procedure for each category:

-	Preparation of Vendor short list (national/international) for equipment and materials.

-	Pre-qualification and preparation of Construction Contractor's short list (national/international) for Contracts.

-	Preparation of General Conditions of Purchase and General Conditions of the Contract.

-	Documents/Drawings Distribution System identifying review/approval/information types.

- Establish procedures for Inventory Management as part of consultancy services.. In case TC/MTC are not available, laboratory testing of materials shall got be carried out by CONSULTANT, cost for which would be borne by BPCL. Visual inspection of the material will also be carried out by Consultant..

- Basic Engineering.

3.1 	Basic Engineering Design Basis

A Basic Engineering Design Basis Document will need to be developed for all the utilities and other underground system required within CCR ISBL. This will also ensure uniformity of the systems and design and enable optimal integration of common utilities, off-sites and general facilities for the CCR complex.

The Basic Engineering Design Basis for the same  will cover but not be limited to the following information:

*	 Definition of the utilities/off-sites.

*	 Location/Site data

*	Seismic considerations and design criteria

*	 Utility specifications

* Equipment design considerations (e.g. economic criteria,      standardisation, constructability issues, sparing philosophy, capacity allowance, etc.)

*	Design guidelines

-    Systems (units) of Measurement

-    Codes and Practices

-    Noise level

-    Maintenance facilities

-    Numbering (coding) systems for equipment,

Pipelines, valves, instruments etc.

-	Legends / symbols for equipment, valves, electrical etc.

-     Insulation

-    Electrical and Instrumentation

- Piping specifications

- Mechanical Equipment

-      Heat tracing

-   Specifications for Civil / Structural work, Buildings (including architectural features).

3.2   CONSULTANT will ensure the design packages for NHT/ CCR from M/s Axens and PSA from M/s LINDE are complete and comprehensive to enable take-off for subsequent detailed engineering. CONSULTANT will carry out extended / residual basic engineering on licensors packages as required such as conversion of M/s Axens/Linde piping specification to be converted to suit PMC pipe lines specifications.

Consultant will carry out the thermal design of air cooler. Licensor will provide the  process specification of the air cooler without consideration on the air side.

Consultant will carry out the thermal design of trim cooler. Licensor will provide the process specification of the trim cooler without considering on the cooling water side.

Consultant will carry out the thermal design of fired heater. Licensor will provide the process specification of the fired heater without consideration on the utility side.

Consultant will carry out the thermal design of Heat Exchangers.  Licensor will provide the process specification of the heat exchangers  without considering on the utility side.

Consultant will carry out the design of  vessels, columns. ,line numbering, etc. & any other additional requirement for detailed engineering. Utility, effluents  distribution lines up-to PLANT battery limits shall be shown in the P&ID’s of the Utility process package and inside the Licensed unit battery limits.

De-superheating required for the steam reboiler will be designed by the Consultant .

-   Environmental and Safety aspects.

3.3	Preparation of Basic Engineering Design Package for utilities & Off-sites shall be in Consultant’s scope of work.

3.4	BPCL has considered the option of designing certain critical equipment/ facilities for a higher capacity, to facilitate ease of expansion in future. CONSULTANT shall carryout the design of these equipments / facilities accordingly.

3.5	All design and engineering will be carried out preferably using the latest version of appropriate standards applicable to Petroleum Industry.

Basic engineering design as well as subsequent detailed engineering and construction will also take into account various statutory requirements/standards applicable to India. A brief list of the same is reproduced below:

a.	Factories Act;

b.	Indian Petroleum Rules;

- Tariff Advisory Committee Guidelines

- Liquid effluent discharge, as per Minimal National Standards for liquid effluents and air emissions conforming to Pollution Control Board Standards;

e.	Civil Aviation Rules;

f.	Indian Boiler Regulation Act;

g.	Indian Electricity Rules;

h.	Requirement of Chief Controller of Explosives;

i.	Oil Industry Safety Directorate.

j.	Other legislation relating to environment protection, such as:

*	Water (Prevention and Control of Pollution) Act, 1974.

*	Water (Prevention and Control of Pollution) Cess Act, 1977.

*	Air (Prevention and Control of Pollution) Act, 1977.

*	Environment ( Protection ) Act, 1986.

3.6 	Consultant’s scope of work also includes preparation of    Process   connectivity / integration   packages   for i) new facilities as a complex ii) new facilities integrated with existing facilities.

3.7	Overall Material and Utility Balance, Catalyst/Chemical Summary

Prepare overall material balance for utilities required for CCR for ISBL and OSBL after adequacy check and residual engineering based on licensors inputs and in consultation with BPCL .

List out with required quantity for all chemicals/catalysts together with their specifications, sources, and rates of consumption. Licensor will  provide requisite details of catalyst.

3.8	HAZOP Studies

HAZOP analysis of process plants, utilities and offsite facilities (including integration/tie-points between various facilities) will be carried out. While all recommendations at ISBL up to mother header in OSBL will be part of this scope; those at OSBL will be implemented by BPCL

CONSULTANT will incorporate the recommendations of HAZOP studies as under;

- HAZOP will be carried out by CONSULTANT after completion of Residual process design for the total Unit including tie-in points for which Licensors presence would be there and the Hazop recommendations would be incorporated by the CONSULTANT.

- HAZOP will be carried out by CONSULTANT after completion of detail engineering for the total Unit including tie-in points for which Licensors presence would be there and the Hazop recommendations would be incorporated by the CONSULTANT.

3.9     Operating Manual:

Prepare detailed and customised operating manuals for process unit, utility and offsite facilities associated to CCR based on the inputs from the licensors, own detailed engineering, equipment vendors and OWNER.

3.10	CIVIL WORKS - SPECIFICATIONS:

CONSULTANT is to establish technical requirements/standards for all types of civil engineering works, raw materials/inputs like aggregate, cement, steel and other materials for buildings, Switch house, Control room ,roads, drainage, plant, OWS system, CBD system well as other construction material.  The sampling/testing procedure should also be established.

CONSULTANT will specify design features for plant/non-plant buildings, structure, taking due care of stipulations of various statutory bodies in respect of compliance with respect to safety, health, etc.

The design concepts should provide both for architectural beauty features and functional requirements to be merged effectively during basic/detailed design of various facilities, keeping in view quality and economy.

3.12	ELECTRICAL SPECIFICATION:

-	CONSULTANT shall collect and compile the load data, the emergency power requirements and assess the electric power requirements of the CCR complex. The same shall form part of Utility Process package (BDEP).

-	CONSULTANT shall review/ estimate the projected load requirements, maximum demand, emergency power, the selection of voltages and distribution network configuration, substation locations etc.

-	CONSULTANT shall review the process operating requirements and classify the electrical loads into critical and less critical according to the effect on plant operation and equipment safety and arrange power distribution accordingly.

-	CONSULTANT shall specify realistic ambient conditions for electrical equipment, considering the Site conditions as well as process originated environments. The switch gear room floor levels shall be located above the highest flood level.  Suitable safety system for pressurised ventilation of substations/switch gear rooms will be provided along with fire alarm & smoke detection system.

-	CONSULTANT shall specify the installation methods of electrical equipment such as cable trench arrangement, method of laying, spacing, marking and termination.

-	CONSULTANT shall highlight in the specifications specific requirements of Indian Electricity (IE) rules, (such as double earthing) and appropriate Electrical Inspectorate's requirements & approval etc.

- CONSULTANT to develop Engg. Standard / technical specification for procurement of different types of electrical equipments to be used in the plant.

CONSTRUCTION POWER & LIGHTING

-	CONSULTANT shall develop the following designs suitable for award of contract:

*	Construction power distribution scheme to maintain uninterrupted tempo of site works. Basic lighting layout, lighting distribution arrangement for approach, plant roads , material storage yards and complete plant etc. to meet the requirements of construction as well as operational phases.

- Basic lighting layout, lighting distribution arrangement for approach, plant roads , material storage yards and complete plant etc. to meet the requirements of construction as well as operational phases.

- System shall be designed in such a way that the same can be used later on for turn around/Shut down.

PROJECT POWER DISTRIBUTION SCHEMES

- -The CONSULTANT shall design the distribution network/s with adequate redundancy with cable routes and sizes, substation locations, HT & LT boards, transformers, UPS, charger, layout configuration, protection scheme, metering, indications, alarm annunciations and earth bus layouts. The additional power requirement for the proposed facilities is about 15 MW. BPCL is augmenting its 22KV power supply system for additional load requirement. It is expected that 22 KV feeders will be made available from Main Receiving Station of BPCL (MR) for CCR project. CONSULTANT scope to include provision of all related electrical system from Main Receiving Station to CCR project facilities including switch house. It is envisaged that new switch house for CCR project would be provided near TDU or in the plot area of IBP-60 sphere area. Proper relay coordination study shall be done to take care of reliability of 22 KV system based on addition of CCR loads.

- Design the distribution network/s with adequate redundancy with cable routes and sizes, substation locations, HT & LT boards, transformers, UPS, charger, layout configuration, protection scheme, metering, indications, alarm annunciations etc.

- Based on additional loads of CCR, requirement of capacitors bank at CCR sub station / switch house.

- Based on the additional loads of CCR the existing load shedding scheme may undergo changes which shall be implemented.

-	CONSULTANT shall design electrical network to provide for unattended substation operation. The metering, relays and other equipment shall be of communicable nature so that the same can be hooked up to the centralised SCADA/MMI system for remote annunciation and operation purpose in future. The new communicable relays shall be compatible to communicate with existing system.

PLANT ELECTRICAL EQUIPMENT

- CONSULTANT shall prepare area classification drawings and specify suitable electrical equipment like motors, field control stations, lighting fittings, communication call points, convenience outlets etc.

Lighting

- CONSULTANT shall specify illumination levels

- (lux levels), the type of fittings to be used for different occupancies and emergency lighting.

Communication system

- Plant communication system to meet the

requirement of the CCR within ISBL.

CONSULTANT shall design the new CCR Plant   communication system for required number of call points to be added in new facility.

Emergency Power

- Emergency power requirements shall include lighting, DC systems & UPS types, capacity and locations including motive load. It shall be met by replacement or addition of existing DG set at Utility block.

Standardisation

- CONSULTANT shall ensure standardisation in lighting fittings, motor frame sizes, cable sizes convenience outlets, DC systems, UPS systems and Plant Communication systems to minimise variety and stocking of spares.

Drawing approval

- All the vendor drawings including package equipment drawings are to be approved BY CONSULTANT in consultation with BPCL.

3.13   INSTRUMENTATION:

- Study and preparation of FF (Field bus) specification.

- Design and construction of new control room or modification of existing control room

- Develop specification for dedicated and editable documentation node.

- Review and approval of all vendor drawings.

Consultant to co-ordinate with licensor during BDEP preparation and include specific requirements, if any for FF control system.

CONSULTANT shall actively participate in the system definition meeting and factory acceptance test of the system.

Design and construction of new control room or modification of existing control room. Development  specification  for dedicated and editable documentation node. Review and approval of all vendors drawings. BPCL to provide specific requirement of additional /indication required in the existing plants arising in lieu of new CCR for inclusion in the consultant scope.

The control system including HC detectors/CCTV/other instrument outputs as required by owner/Licensor shall be housed in a new control room or expansion of existing C/R, to be designed by the CONSULTANT.

The control system defined by CONSULTANT should be interfaced to the data networks of the ERP and MES for a duplex communication.

BPCL shall provide necessary inputs including inputs for driver software & process optimisation.

CONSULTANT to define/evolve a suitable Engg. Design basis for all types of Instrumentation and Control Systems/equipment, which may be plant specific. This may define: Type of digital control system (DCS), Redundancy concept in control/data acquisition system, Type of operator interface, Type of Advanced control/optimisation interface with DCS, Type/Concept of different layers of control/MIS/ Optimisation/LAN/WAN, Type of different field instruments viz. Transmitter, I/P converters, control valves, Pressure/ temp. gauges/switches shutdown valves, analysers, actuators etc.

CONSULTANT to  define  Process optimisation philosophy and its integration to DCS. CONSULTANT to define the type of computer environment required for Process optimisation (Advance Process Control).

CONSULTANT to define guidelines for different safety  instrumentation in plants covering both process plant safety and human safety.  CONSULTANT should define an integrated fire fighting system in which hydro-carbon  detectors ,H2S detectors , fire detectors and smoke detectors etc., shall be a part of the system along with a plant wide network.

CONSULTANT to define guidelines   regarding  requirement of type of instrumentation/automation for Product transfer.

CONSULTANT to develop Engg. Standard / essential technical specification for procurement of different types of instrumentation and control equipment to be used in the Refinery including analytical and pollution control instruments. The standard/ specification should take care of PROCESS LICENSOR / CPCB specific requirement, if any.

In case of CONSULTANT is augmenting existing facility or providing additional facilities in existing plants, engineering of instrumentation and control system for the same shall be carried out while integrating the new facilities with the existing units.

CONSULTANT to define installation and Loop checking concept of different types of instrumentation based on application.

CONSULTANT to define C.C.T.V. system to monitor flare and other critical system in various new units.

CONSULTANT to  recommend  both on line as well as offline analyser requirements along with their sampling systems.

CONSULTANT shall supervise the installation carried out by the site contractor and provide necessary assistance for commissioning activities.

ONSULTANT shall develop specification for dedicated & editable instrumentation documentation node with necessary software, which shall store all plant instrument (field & DCS) related documents. The node shall be database type having link with various instrumentation documentation (like inst. index, loop drawing, JB details etc) and DCS documentation.

Detailed Engineering

The following activities shall be carried out by   CONSULTANT :

Instrumentation

- Preparation of Engineering design basis for instrumentation.

- Sizing calculation for orifice plates/ flow elements, control  valves   and pressure relief valves.

- Preparation of specification for field instruments and FF based         DCS.

- Preparation of MR for instruments/ DCS and PR indicating makes and model no of instruments.

- Preparation of two years operation spare list (instrument wise) with OEM part no.

- Preparation of tender specifications and technical evaluation / recommendation.

- Installation sketches and wiring diagram.

- Preparation of logic diagrams with cause & effect table.

- Preparation of functional schematics, complex schemes with write up, if required.

- Preparation of field engineering input for DCS such as point data base, graphics, auxiliary console layouts.

- Preparation of instrument index.

- Review and approval of vendor drawings.

- Hydrocarbon / hydrogen / fugitive emission leak detection system as required / identified at critical location.

- Preparation of all construction drawing related to field instruments                  such as:

- Cable duct / main trench, IRC lay out drawing

- Junction box and instrument location layout.

- Air supply distribution drawing.

- Instrument installation drawing.

- Instrument hook-up drawings.

- Preparation of BOM for field instruments installation.

- Preparation of SOQ for instrument erection work.

- Preparation of field cable schedule.

- Calibration of instruments, hydro testing of impulse lines.

- Installation and supervision of instruments, DCS.

- Loop checking of field instruments from field instruments from field to control room in coordination from DCS vendor.

- Sizing of instruments.

- Layout plans.

- Sequence / functional logic for DCS.

- Material take off for procurement.

- Review and approval of vendor drawings including LSTK & package vendors.

- Preparation of detailed specification for the documentation node with necessary software. Define and generate the input required for the documentation node software.

3.14	Operating Costs:

The cost of production will be tabulated by CONSULTANT taking all relevant factors into consideration. CONSULTANT shall work out the operating cost in standard CONSULTANT format as part of cost estimation/updation.

3.15    Equipment layouts:

Considering the limitations of space for the project execution, CONSULTANT shall optimise on the equipments layout for  the CCR complex / facilities taking into consideration the OISD, licensors and any other statutory guidelines/stipulations including state and central government.

3.16   Fire Protection:

CONSULTANT shall specify the fire protection requirements both passive and active for the Project facilities which includes fire alarm and  smoke detection system for unit sub-station, if required.

4. 	Project Implementation

CONSULTANT shall perform the SERVICES AS UNDER as minimum requirement:

4.1      Residual Process Engineering

CONSULTANT shall carryout:

### Coordination  with the licensor M/s Axens/Linde for preparation of BDEP and subsequent Process & Detailed engineering.

### Most of P &IDs of existing units are available. Tie up details shall be incorporated in the existing P&IDs.

### Updating P&ID’s for CCR complex including incorporating line numbers, PMS indicating piping specs tie-in pts., engineering inputs for detailed engineering.

### Hydraulic check for all lines and control valves etc. by carrying out piping study based on layout & P&IDs  to ensure line sizes considered  are correct.

Preparation of Piping Material Specification in line with that of Licensors..

Preparation of utility distribution diagrams and P&ID for utilities within ISBL and up to mother header in OSBL upon adequacy check..

Sizing of control valve & assemblies.

Numbering of level gauges, RO, sizing and associated PSV inlet / discharge  pipe lines.

Drain details of pumps and exchangers.

Sizing of utility lines.

Number of shells of exchangers, bundle details of air-coolers.

Heater process detail  including Heater API   datasheets

### Updation  of  P&ID’s including incorporating line numbers, engineering inputs for detailed engineering.

- Prepare PFDs for utilities within ISBL and up to mother header in OSBL upon adequacy check.

4.2    Detailed Engineering

The following activities shall be carried out by CONSULTANT :

## Engineering Design Basis:

CONSULTANT will develop Design Basis taking into consideration Owner’s specific standards for carrying out detailed engineering in order to ensure adoption of uniform practices for all the units/systems; as a minimum covering the following:

*        Codes and standards

Piping material coding and specifications.

Compare PMS / VMS based on details given by   Process Licensor and incorporate in the P&ID based on this master list

*	Detailed specifications for civil/structural works including architectural features, foundations, fire proofing, pipe racks, including operating platforms, approaches, etc.

*	Fire protection system guidelines

- Mechanical Specifications

- State of art engineering, design practices for all equipments and optimization of all utilities

*	Electrical specifications

*	Instrumentation specifications

*	Insulation and painting requirements

*	Requirements of state and central government  statutory authorities with respect to drawings, specifications and documents.

General Civil

- Development of site grading  plan and fixation of levels. Site

- Development of plot plan.

- U/G piping in the ISBL & OSBL and hook-up with the existing facility. BPCL to provide process parameters at interface points.

- Site work for grading, in plant roads, drainage / sanitary system.

- CBD,OWS AND CRWS

- Internal roads and drainage including culverts shall be provided as per site requirement..

- Design and construction of Electrical Substation, Cable trench, pipe bridge, road crossing

- Fire water network within the unit is part of the scope. The requisite adequacy check of the supply header shall be carried out forming the ring encompassing the unit with two hook ups. For this water requirement for other units within this ring will be provided by BPCL.

- The console for CCR shall be housed in the existing DHDS control room with requisite modification and back up panel shall be located either  by extending the blast proof RMP control room with necessary modification or in a new blast proof rack room.

- Cooling water shall be raw water. The supply and return header along with cooling tower shall form part of this scope.

- For OWS the requisite UG collection and pumping shall be provided with lines up o the mother header.

- Inter roads, drainage including culverts shall be provided as per site requirement.

- Design and construction of Electrical Substation and Blast Proof Control Room as per requirement.

- Necessary inputs with specifications will be provided to award the job for Soil investigation shall be provided. Experts will be deputed to site as required during this job and the results will be evaluated.

- Prepare GADs ,3D model in PDS/PDMS for piping , civil including underground piping.

Structural Engineering

- Design and preparation of detailed drawings for foundations, structures, platforms and ladders (Detailed fabrication drawings are part of the execution contractor’s scope). However, some shall be reviewed and approved by PMC.

- Drawing shall be as per statutory norms of CCOE, Municipal  Corporation, Factory Inspector, DISH etc.

- Material take off for cement and steel for emergency / urgent contracts lined up at site.

- Control room, Electrical substation as per requirement

- Preparation of tender specification and technical evaluation / recommendation.

- Review and approval of contractor’s drawings.

Static Equipments:

- CONSULTANT shall carry out the thermal design of air fin coolers etc., mass transfer design of static equipments, line numbering, etc. & any other additional requirement for detailed engineering.

- De-superheating required for the steam reboiler will be designed by the CONSULTANT

- Preparation of tender specifications and technical evaluation / recommendation and also carryout FEM analysis of critical items if required.

- Carry out mechanical design in accordance with various codes, to suit the process operating conditions including material specifications.

- Preparation of design drawings for fabrication.

- Review and approval of vendor’s drawings.

Heat and Mass Transfer Equipment

- Thermal design.

- Mechanical design.

- Preparation of tender specifications and technical evaluation / recommendation.

- Review and approval of vendor’s drawings.

Rotating Equipment

- Specifications for individual pumps, compressors, blowers, fans, turbines, along with drives and their accessories etc.

- Preparation of tender specifications and technical evaluation / recommendation.

- Review and approval of vendors drawings.

Piping

- Preparation of  VMS (valve material specification) and PMS (Piping Material Specification).

- Preparation of equipment layout.

- Identification of Hook-up points along with BPCL and preparation of engineering drawings for construction including material take off.

- Material take off as required for the PROJECT.

- Preparation of GAD’s, isometrics etc.including 3D modelling in PDS/PDMS..

- Preparation of tender specifications and technical evaluation / recommendation.

Prepare 3D modelling and review with Client/Licensor at 60%    and 90% completion.

Organise 3D model walkthrough for Process Licensor as a part of pre commissioning check after completion of piping engineering.

- Underground piping Layout within ISBL with requisite 3D model in PDS.  Consultant shall organise 3D model walkthrough for Process Licensor as a part of pre commissioning check after completion of piping engineering.

- Consultant shall check the hydraulics of the engineering piping/equipments.

Electrical Engineering

- Prepare single line diagram.

- Material specifications for all electrical equipments, repaired for the project in consultation with BPCL. Preparation of tender specifications, technical evaluation / recommendation.

- Detailed load study for the existing switchgears/systems, UPS / DC power requirement, design for modifications, if required, preparation of interconnection diagram for hook ups with the existing system.

- Design for Plant communication system for the number of call points and their locations finalised with OWNER.

- Augmentation, if required in the upstream / switchgears of hook up locations (affected portion).

- Materials take off for procurement.

- Modification in the present load shedding scheme based on additional loads of CCR.

- Electrical load, earth grid layout drawing, cable trench layout drawing, lighting layout in PLANT & substation, offsite area.

- Cable sizing calculation, cable layouts, cable schedule, interconnection diagram, relay coordination for the new facility as well as upstream facility.

- Transformer sizing calculation based on complete load details of CCR project.

- Cable sizing calculation, cable schedule for complete CCR project.

- Based on the additional loads of CCR the existing load shedding scheme may undergo changes which shall be implemented by BPCL and input by consultant.

- Preparation of specification for all the electrical equipments required for the project in consultation with BPCL.

- Preparation of tender specifications, technical evaluation / recommendation.

- All the vendor drawings including package equipment drawings approval in consultation with BPCL All the major electrical equipments are to be procured & shall not be part of contactor’s scope of supply.

- CCR unit shall be provided with the lift for the tallest column.

- Preparation of tender specifications for site activity, technical evaluation / recommendation.

Insulation and Painting

- Sizing.

- Preparation of insulation list and specification for construction

- Preparation of tender specifications and technical evaluation / recommendation.

Package Units

Review of vendor / contractors design specifications for packaged units from the point of view of suitability and conformity to the project specifications, ease of operation/maintenance and quality control of the sub-components.  For an overall control, a stage wise approval from the CONSULTANT should be specified for all such package units i.e. at stages of detailed design and manufacture.

Chiller : The propane package units proposed by the Licensor  will be design by the consultant. Licensor will provide the process specification of the chilling exchanger without consideration on the propane side.

All other package units as specified by Licenser such as Chlorination Agent Injection Package, Oxy-chlorination water Injection package, Caustic Injection Package, heaters in Regeneration circuit, Dryer and other items as specified by licensor  to be design by the consultant only.

Consultant shall execute the regeneration of catalyst job as a package.

Corrosion Protection & Inspection Requirements

CONSULTANT will be required to specify suitable measures for corrosion protection of material/equipment for all the services involving corrosive media and also ensure suitable provisions are made for installation of “inspection facilities” in most vulnerable locations to assist in online inspection and condition monitoring.  Corrosion probe/analyser will be foreseen by the consultant in consultation with the Licensor.

4.3 	Safety/Environmental Engineering

CONSULTANT will consider and incorporate major features necessary to ensure the safety of the PLANT and personnel. CONSULTANT will take into consideration local and international standards pertinent to pollution and environmental control, including effluents and solid waste, atmospheric emissions, noise control etc.

-	  Catalyst Loading and offloading system.

-  Gas/ Liquid/solid waste  disposal facilities, including discharge route/point for liquid effluents.

-    Air pollution control measures/monitoring system.

-    Noise pollution control measures/monitoring system.

Safety supervision shall be part of this scope.

4.4    Procurement  Services

- Preparation of procurement procedure in consultation with BPCL

- Preparation of a comprehensive vendor list & the approval for the same to be taken from OWNER.

- Issue of enquiry to approved vendors , evaluation of bids, recommendation to BPCL and preparation of draft TOI/PO.

- CONSULTANT shall provide item wise cost estimates for all tag items. Estimates should also be provided for all single bid items.

- Cost estimate shall be provided for all tagged items including specialized items such as control valves except other instrument tags.

- Cost estimate for single vendor case only for procurement items.

- All procurement & tendering services to follow BPCL General Purchase Conditions and General Contract conditions

- Procurement / tendering on limited tender basis including for specialized jobs. However  for tenders/ procurement above Rs. 5 crores existing tendering guidelines of BPCL shall be followed.

- Centrifugal compressors and reciprocating compressor would be endeavoured to be procured within maximum 16 months from the date of award of contract. The delivery of the CCR reactor would be maximum 18 months from the date of award of vendor.

- Review quoted delivery dates to ensure compatibility with the approved Project schedule and ability to meet site material requirements during the construction phase.

- Expedite vendors for timely deliveries and Closely monitor actual delivery dates and ensure adherence to expediting functions and prepare plans for remedial actions in case of any delay foreseen in delivery of equipment/material.

- Review and approve the Quality Assurance and Control procedures proposed for the PROJECT.

- Ensure that the inspection and quality assurance programs are being followed and that proper documentation is provided for all equipment and bulk materials.

- Monitoring of fabrication of equipment and materials.

- Require the immediate reporting to BPCL  of all changes which will affect material quality, and recommend any necessary corrective actions to be taken.

- Analysis and trouble shooting for corrective actions to ensure timely delivery.

- Ensure submission of As-built documents.

- Review and approve the material movement and handling procedures proposed for the PROJECT.

- Recommendation on the performance of the vendors leading to closing of the contract.

- Arrange customs clearance and transportation of materials to site through contractors.

- Ensure that an accurate and traceable listing in the procurement records for the location, quality, and character of all permanent materials in the PROJECT is being maintained.

- Co-ordination with all transporters for shipping/transporting of equipment/material to BPCL site from vendor’s works wherever supplies are based on FOB/Ex-works basis.

4.4.1   Inspection / Expediting

Inspection of all indigenous items will be done by CONSULTANT. Expedite vendors for timely deliveries of equipment / bulk material and closely monitor delivery dates. Prepare plans for remedial actions in case of any delay foreseen in delivery of material.

Monthly progress status report shall be obtained from all the critical vendors and to be submitted to BPCL along with consolidated monthly status report of all procurement items (equipment / bulk material) prepared by CONSULTANT. Foreign inspection of imported items is excluded from  Consultant’s scope. However, expediting of foreign orders is included in Consultant’s scope. CONSULTANT shall utilise his local offices in foreign countries for necessary expediting visits locally for which all charges are deemed to be included in Bidders price. In case of requirement of foreign travel, approval shall be sought from OWNER and foreign travel expenses shall be reimbursed at  actuals. However CONSULTANT’s lumpsum fee shall include foreign travel charges towards visit of CONSULTANT engineers to Licensors offices for review of P&ID’s only.

4.4.2  Third  Party Inspection

Provide all requisite inspection services for all indigenous equipment / bulk material procured for the project as part of EPCM services at no additional cost. TPI if any decided by owner will be born by BPCL.

For imported items, the bidders will be asked to indicate separate third party inspection charges, which will be considered for evaluation of prices and included in the order value at the time of award of order.

4.4.3 	Procurement of Initial Spare Parts and Operational Spares

CONSULTANT will review and recommend to BPCL for approval the quantity of Initial Spare Parts which, in the opinion of CONSULTANT, will be adequate for first 24 months of operation and maintenance from start-up.

CONSULTANT will assist in evaluating and confirming reasonableness of the price quoted for these O&M spares. CONSULTANT will ensure that all identified/ordered spares are delivered in time for start-up/commissioning.

4.4.4	Commissioning Spares

CONSULTANT will review and ensure that vendors/contractors provide for all required spares/replacement components that may be required during pre-commissioning and start-up activities of the PLANT.

4.5     Tendering

- Preparation of tendering  procedure in consultation with BPCL

- Evaluation of tenders and recommendation to BPCL for award of the contract. CONSULTANT shall furnish item wise estimate in line with SOR with each tenders recommendation.

- Draft contract preparation and assistance in sorting out contractual problem during execution.

- Time limit for approval / comment  of drawings / documents by CONSULTANT shall also be within 10 calendar days.

- Drawing approval of critical equipment / after first comment shall be across the table.

4.6   Billing

Certify the site work along with deductions as per contract for billing purposes as per prevailing procedure adopted during other projects

CONSULTANT shall evolve a billing schedule and recommend to OWNER for acceptance. CONSULTANT shall cause the contractors to submit the running bills in the acceptable formats and shall certify/recommend for payment by OWNER.

CONSULTANT shall assume complete responsibility in settling extra claims by the contractors .

The final bill of contractor will be recommended for payment  by CONSULTANT after ensuring that all of the contractual obligations have been fulfilled including supply of spares, as-built documentation etc.

##### 4.7    Ware-House Management

Complete warehouse management shall be as per earlier BPCL jobs.  i.e as per RMP and CRU Project.

Co-ordination with contractors for various related services such as those required for receiving, movement, handling and transportation of materials.

Prepare and submit weekly report of material issue and receipt.

All transactions related to receipt and issue of material after purchase orders such as material receipts / issues, reconciliation, capturing CENVAT details from vendor’s invoice etc. will be required to be carried out in the BPCL’s ERP system (SAP)  by consultant. CONSULTANT shall deploy personnel with SAP MM module experience. Necessary user licence/ training shall be arranged by BPCL.

Ensure collection of all Cenvatable invoices from the transporter / supplier while receiving the material and shall pass on to BPCL on day-to-day basis and within 24 Hrs. of receipt.

Material shall be despatched on FOT site basis and payment will be released within 2 weeks. Deviations to this may be looked into on specific cases.

##### 4.8    Inventory liquidation

CONSULTANT shall formulate systems to manage and  utilise the existing surplus inventory. No new order shall be placed unless availability of item(s) in existing stock is explored and a  certificate to this effect i.e., ‘checked & not-available in existing stock’  is issued by CONSULTANT against each recommendation.

Further CONSULTANT shall take all precautions and due care to ensure that the surplus material generated against the PROJECT  will be minimum. It shall be the CONSULTANTs responsibility for liquidation/disposal of owners surplus material generated against the PROJECT scope of work. CONSULTANT shall forward the list of surplus inventory to other Consultant’s clients to check if any of the items are useful to them, prior to disposing off the same to local traders/agencies by inviting bids and considering the best offer received.

##### 4.9    As-built drawings of existing facilities

As built “drawings / details will be provided to the extent possible. CONSULTANT shall physically check at site and prepare drawings.

5.	CONSTRUCTION MANAGEMENT

CONSULTANT will be responsible for effective monitoring of all construction areas of the PROJECT for which purpose, it will establish requisite site organisation staffed by competent and experienced specialists. Requisite number of specialised personnel shall be provided to site, as and when necessary. Construction management services shall include but not limited to the following:

5.1 	Construction Planning & Procedure

-	Finalise co-ordination procedures between BPCL, CONSULTANT and  Contractor’s from time to time.

-	Establish detailed construction plans and schedules with  contractor’s to match the overall Project schedule.

-	Identify construction / field organisation of contractor’s / CONSULTANT.

-	Finalise construction codes, standards and specifications to be followed.

-       CONSULTANT shall conduct regular safety meetings. Safety MIS shall be provided to BPCL. On site supervision shall be provided by qualified safety personnel at ISBL and OSBL. No. of safety supervisors shall be based on the activity.

5.2 	Construction Schedule,  Monitoring , Management & Quality Assurance

- Review construction schedule of contractors work at site.

-	Review site mobilisation plan and pursue for required mobilisation for all manpower / resources / equipment etc.

-	Monitoring contractor's work schedule, progress against program and preparation of monthly progress/exception reports highlighting percentage completion of work, areas of concern with respect to schedule/inputs to be deployed and recommend proactive corrective actions and remedial measures to remove back-log in progress. Distribution of reports / construction documents to all concerned.

-	Review the construction work/progress regularly to ensure that the Contractor's allocation of numbers and type of manpower is adequate, and to ensure that construction equipment, cranes, tools, scaffolding, lighting, etc. for the execution of the work are adequate and in safe working condition.

All material handling equipment should be subjected to required load test, initially and then periodically, to ensure safe/stable operation; CONSULTANT to witness and maintain record of all such tests.

-	Review and approve the drawings and technical specifications produced at site by the Contractor to ensure compliance with the Project specification.

- Verify the actual work completed by the Contractor and recommend to BPCL for release of each progress payment according to the contract. Monitor closely the value of work done so  that  the final bill value including extra works shall  not exceed the contract value. CONSULTANT shall be responsible to   forecast and award new contracts for the balance work (any revision in the contract value for item rate contract must be brought for BPCL’s approval at-least 2 months prior to forwarding the contractor’s bill of payment. The variation in quantities may be handled with the contractor as per standard practises and variation limits or separate tendering may be resorted to based on the conditions prevailing).

- CONSULTANT shall cause the contractors to submit the final bills and with in 15 days of completion of work shall forward the recommendation to OWNER for release of payment. CONSULTANT shall process recoveries from contractors for issue of materials, hire charges, rents and taxes etc as per provision of contracts. Where ever required CONSULTANT shall deal with contractors for  expeditious settlement of extra claims, disputes etc.

-	Review of construction and quality assurance plans of Contractors, and confirm their compliance to approved codes/standards/ specifications, etc. under the contract.

-	Supervision, inspection and certification of quality and quantity of work performed by contractors at Site.

-	Review and audit approved welding procedures and welders qualification procedures.

-	Monitoring, controlling and co-ordination of all tests (destructive/non-destructive) at site, analyse and certify results.

- Monitor compliance of various statutory rules, regulations and safety measures and also arrange and co-ordinate site inspection, testing, etc. as required under local statutory rules and regulations prevalent in India; provide technical assistance to BPCL in obtaining various statutory approvals / clearances.

- Provide assistance to BPCL in matters pertaining to local laws, labour and public relations.

-	Ensure that the Contractor/ other contractors take all necessary precautions to protect construction work and material from damage by climate elements and construction activities.

-	Supervise and ensure that all works or modifications that have been approved by BPCL are performed according to approved specifications.

-	Ensure that machines, equipment, vessels, piping, instruments, structures and other materials are properly erected, installed and maintained according to the approved specifications/suppliers recommendations.

-	Review, recommend and monitor safety and labour relations procedures prepared by the Contractor for compliance with applicable codes, regulations and BPCL requirements and advise concerning violations and injuries (including co-ordinating with local concerned authorities).

-	When any part of the PROJECT is completed and operating while others parts of the PROJECT are under construction, CONSULTANT will review the safety rules prepared by the Contractor and ensure that all required rules/ regulations are adhered to.

-	Inspect all of the Contractor's site activities, which include recording, field purchasing etc. The following data and files will he collected and recorded:

*	Engineering data

*	Contractor daily manpower loading reports

*	Welder's qualification certificates

*	Equipment transportation, deliveries and

receiving reports

*       Data for as-built drawings.

-	CONSULTANT will cause contractor to submit detailed scheme/s for heavy/critical equipment's erection/ lifts/rigging and review/approve them before contractor effects such activity.

-	CONSULTANT will supervise and approve alignment (hot/cold) of all rotary equipment/machinery by contractor and also ensure their upkeep/maintenance as per suppliers' recommendations.

-	Require the Contractors to perform house-keeping activities which include maintaining sanitary facilities, sweeping, clean-up, removal of excess materials/ temporary/ facilities, scaffolding, as necessary.

-	Formulate a system to identify and correct the Contractors work that may be unsatisfactory in quality, and/ or is not conforming to the contract so that the Contractors will be properly informed in a timely manner. Ensure that adequate records are maintained, so that of rectification is made easy, systematic and timely.

-	The quality control program prepared by the contractors will be reviewed to ensure that it covers the following areas:

*       Site preparation

*       Welding/fabrication

*        Tie-ins

*        Clean-up, testing

*        Buildings and structures

*        Instrumentation installation and construction

*        Incorporation of all witness tests and hold points

of the construction work.

5.4 	Construction Inspection :

The CONSULTANT will ensure that the contractors make arrangements for the required field inspection and tests required by the standards/specifications under the contract and by local authorities/ agencies and submit inspection procedures.

CONSULTANT will ensure that these Inspection procedures will at least including the following requirements:

-	A construction activity will not start until all prescribed quality preconditions and prerequisites have been met.

-	The contractors will not proceed beyond identified witness tests and hold points without Consultant’s clearance. The CONSULTANT will plan their activities to prevent undue delays in inspection at these points. Construction schedules shall allow a reasonable time for inspection, as required.

-	If it is observed that work is not conforming to specifications and drawings, CONSULTANT will promptly bring this information to the attention of the contractor concerned and will ensure that remedial works are carried out.

-	In those situations where continued work would cause damage, preclude further inspection, or make remedial action ineffective, and where there is no authorised representative of the contractor immediately available at the work location, Consultant’s inspector responsible for that work will have the authority to stop the work in progress. He will immediately notify OWNER and the concerned contractor of such action.

CONSULTANT will:

-	Witness all field inspections and tests that are necessary to comply with the Project specification.

-	Witness, review, analyze, and certify all proof of proper construction provided by the contractors to ensure compliance with the Project specifications.

-	Witnessing & certifying final inspection (i.e. physical check) of equipment after erection at site.

-	ensure that the number of welds to be spot checked is a true representation of the actual number of welds.

-	ensure that the contractors maintain a proper and up-to-date documentation system of the radiographs which can identify the location of the weld and the welder concerned.

-	ensure that all inspection reports and files with proper cross identification with field materials are handed over to OWNER within one (1 ) month after completion of Mechanical Completion of any part of the PROJECT.

-	Witness, monitor and ensure that all field inspection by the contractors for mechanical equipment, civil materials and electrical equipment will adhere to the procedures laid down in the Project specification.

-	ensure that erected equipment conforms to the flow diagrams, construction drawings, manufacturer's , and the Project specification.

5.5	Organise field engineering work, wherever necessary and provide assistance to BPCL in timely resolving of Site problems / constraints.

5.6    Witness hydro-test, pneumatic and other field tests and confirm successful completion of the same.

5.7	Approve erection plans, establish safety plan and supervise activities for all erections. Ensuring safety at construction site will be the responsibility of CONSULTANT. Any problem encountered will be brought to the notice of the OWNER for a solution.

5.8	Mechanical Completion

Project schedule shall be 26 months from the zero date. The date of

Handing over of critical equipment datasheet shall be considered as zero date for project schedule.

CONSULTANT will develop a phased mechanical completion program to facilitate sequential pre-commissioning activities in a logical manner.

CONSULTANT will ensure that the contractors submit the Systems Completion Manual, which will contain a checklist of forms and procedures for systems testing to achieve Mechanical Completion. CONSULTANT will review this Systems Completion Manual and recommend to BPCL for approval.

Initiate action for arranging the services of vendor’s specialists as required for satisfactory execution of erection and mechanical trial run, in terms of respective contract.

CONSULTANT will ensure that all parts of the PROJECT have been mechanically erected and that all systems testing have been carried out satisfactorily in line with Licensor and according to the approved Systems Completion Manual and start-up schedule. CONSULTANT will review the punch list in line with the licensor/owner all incomplete work and un-rectified/un-attended deviations to ensure that such work is performed (unless waived by BPCL) before the certificate of mechanical completion can be issued.

Coordinate with Licensor/Owner and ensure completion of all punch lists.

6. 	SERVICES FOR PRE-COMMISSIONING  & COMMISSIONING

During this phase, CONSULTANT shall provide necessary assistance to BPCL in planning and organising pre-commissioning, commissioning, start-up and performance test run of the Project facilities, in due co-operation with Licensors and other contractors. The Consultant’s scope of work, will comprise of but not limited to, the following:

*	Set-up, review and implement start-up program.

*	CONSULTANT shall prepare a detailed operating manuals for each system / unit based on in-house data, licensors manuals / information, data from equipment vendors etc.

*	Prepare pre-commissioning, commissioning and standard procedures for start-up, normal operation, shutdown and handling of abnormal situation considering input from Licensor.

*	Co-ordinating and supervising commissioning schedules, start-up schedule. etc. with contractors and others.

*	Preparing punch/check lists for verifying mechanical completion.

*	Conduct safety audit of the erected PLANT, unit wise and prepare checklist before pre-commissioning activities can be started.

*	CONSULTANT will perform comprehensive pre-start-up inspections of all completed equipment and systems and supervise all activities for equipment check-up including certification of its proper functioning.

*	CONSULTANT will ensure that the Contractors provide sufficient manpower, special tools and spare parts necessary for assisting commissioning activities such as:

-	Operational tightness testing.

-	Pre-start up inspections by governmental bodies, as necessary.

-	Loading of catalysts & chemicals.

-	Filling of lubricants.

6.1 	Ensure that all the pre-commissioning/commissioning activities of the PROJECT are carried out by contractors in accordance with established procedure, schedules and program, as detailed below:

-	Equipment operation to make checks of vibration, governor trip, and safety device, and other required operating tests and adjustments.

-	Hot alignment checks and running of component parts as a unified system.

-	Adjustments and replacements, if necessary, of mechanical seals, packing and accessories as required.

-	Flushing, blowing and chemical cleaning.

-	Installation of temporary screens, strainers, and blinds.

-	Necessary purge operations, including installation of temporary purge piping or hoses to equipment connections.

-	Checking of bores of orifice plates and installing them after flushing operations.

-	Functional check on all instruments and controllers.

- Instrument calibrations with standard test equipment and all required adjustments and control point settings.

-	Check all instrument loops for proper functioning.

-	Checks on pipe hangers, supports, and guides for hot/cold settings and necessary adjustments.

-	Checking and recording positions of all valves.

-	Drying of refractory of exhaust stacks and heat recovery sections by firing temporary burners, if applicable, in the presence of vendor's representative(s).

-	Conduct simulation runs to allow run-in and operational testing of the equipment.

-	CONSULTANT will ensure that all defects and deficiencies found during the course of pre-commissioning shall be rectified by the contractors.

6.2 	Testing

The following work will be performed by CONSULTANT until the Project is ready for commercial operation:

*	Supervision/ monitoring of check-up and calibration of the various instruments to be used in plant system commissioning and testing.

*	Supervision of all activities for commissioning and testing of various sub-systems and of the whole system, all in accordance with the start up schedule.

*	Development of criteria for Initial and Final Acceptance.

*	Analysis and evaluation of the test results obtained during testing and commissioning in order to determine actual performance of equipment, sub-systems and the whole plant against both construction contract requirements and Licensors /Contractor(s) guarantees.

*	Preparation of a checklist of all defects, deficiencies, shortages etc. and development of a program for their correction and completion.

6.3 	CONSULTANT will advise BPCL the review and approval of performance test procedures provided by contractors/ licensors and specify, among other things, the following:

-	Operating data to be recorded in a log sheet

-	Sampling methods

-	Analytical methods

-	Methods of calculations

-	Interpretation and measurement of tests

-	Manner of taking operating data and its frequency

-	The manner of evaluating the performance of the unit, raw material consumption, utilities consumption and energy consumption, yields etc. including appropriate corrections if any for test conditions such as feedstock quality etc.

6.4 	Ensure that performance test of all units are performed in accordance with professional engineering standards, plant safety and operating standards.

6.5 	CONSULTANT shall arrange and organise for the performance guarantee tests. However they shall be performed by the operating staff of BPCL, in presence of respective Licensor/Consultant personnel. On completion of performance test runs, CONSULTANT shall associate with the licensor to prepare the remedy report for BPCL on performance of each unit with recommendations (in consultation with Licensors and BPCL) on ways and means of improving performance, if necessary.

6.6 	CONSULTANT will evolve acceptable formats for handing over of plants to BPCL including all required documentation, completion certificates etc. and shall recommend to BPCL regarding taking over of facilities.

6.7 	Spare Parts:

The following will be performed by CONSULTANT :

*	Checking of spare parts and other supplies to be made available by the contractor(s) to ensure compliance with the construction contract requirements and supervision of their handing over to BPCL.

*	CONSULTANT shall provide necessary assistance to BPCL for spare parts inventory and future ordering schedule for safe conditions/trouble free operation.

B.       DOCUMENT CONTROL REQUIREMENTS

1.0 	Introduction

The procedures depicted herein define the minimum requirements for the control of CONSULTANT information/work to be supplied in accordance with the Contract. CONSULTANT shall develop a Document Control Procedure consisting of the requirements set forth herein and in the Contract documentation.

CONSULTANT shall provide information to OWNER for review and/or approval describing the design, manufacturing, installation, testing, quality, control/assurance and other items for work set forth in the Contract documentation.  Additionally, CONSULTANT shall provide to OWNER a CONSULTANT Document Register depicting the submittal review and approval cycle.  The format of CONSULTANT provided information shall be in accordance with the requirements depicted herein.

2.0	CONSULTANT  DOCUMENT  REGISTER

Notwithstanding any other requirements of the Contract, CONSULTANT shall prepare and maintain a register of all documents deliverable under the terms of the Contract. The register shall include but not be limited to the following information:

- Document Title;

- Document Number;

- Revision Number;

-	Start Date - Planned/Forecast/Actual;

-	Issued for Review Date - Planned/Forecast/Actual;

-	Issued for Execution - Planned/Forecast/Actual;

-	Percent Complete

-	Cross References - Document Numbers

The register shall be broken down in accordance with the major activities of the Schedule of Work.  The physical percent complete of each document, when aggregated in accordance with an agreed weighing shall define the percent progress of the major activities.

The register shall be agreed and issued within Thirty (30) working days after award of Contract.  If no agreement is reached within twenty (20) working days after award of Contract, OWNER may direct the list of documents to be included from time to time during the Schedule of Work.  The register shall be updated by CONSULTANT periodically to reflect the current status/revision of each document or drawing including additions and deletions and issued weekly to OWNER unless otherwise agreed in writing with the OWNER.

The register shall be capable of being sorted by relevant Project Section such that all documentation applicable to a particular Section may be listed together and reports issued accordingly as and when directed by OWNER.

During construction operations, CONSULTANT shall transmit a weekly fax to Owner’s designated office and worksite to confirm/update the status of documents in use at the Owner’s office and at the worksite.

3.0 	Project Document Numbering

CONSULTANT shall number all documents, drawings and procedures in accordance with an agreed document numbering system.  The file name of electronic copies shall be similar to the relevant document number for easy cross-referencing.

All documents issued shall follow a structured revision numbering sequence.  The revision numbering system shall be included in the Document Control Procedure submitted for review and/or approval by OWNER.  The document revision number shall be clearly indicated on the original document and within the electronic file name.

4.0	Times for Submission

The planned dates for document issue shall be in accordance with the approved Schedule of Work including due allowance for OWNER review and approval.

Further submissions shall be made in accordance with the following:

Item/Manual                Submitted by CONSULTANT after Award

-   quality  plans          90 days prior to commencement of each activity;

-   quality  assurance          within 30 days after Contract

procedure			award

-   document  control            within 30 days after Contract

procedure.                      award;

-   equipment  testing/          within 30 days after completion

final inspection report     of testing

-   as-built drawing and        within 30 days after completion

as-built report                  of construction activities

-   HSE Manual                   30 days after Contract award.

C.  PROJECT CONTROL REQUIREMENTS

1.0	General Requirements

These requirements specify Owner’s requirements for the planning, scheduling, cost control, and reporting activities, which CONSULTANT shall perform as part of the WORK.

2.0	Approvals

2.1.	Within thirty (30) working days of Contract award, CONSULTANT shall establish subject to OWNER approval a weighting basis, which will show the percentage weighing for each work activity within each area of the work.

2.2	Within thirty (30) working days of contract award, Consultant’s control and progress measurement systems shall be fully operational, incorporating all data and demonstrated to Owner’s satisfaction.

2.3	CONSULTANT shall, when instructed to by OWNER, prepare and submit to OWNER for approval, a revised Schedule of Work.

3.0	Planning/ Scheduling and Reporting

CONSULTANT shall present a detailed actual status of the work  in the form of a written Monthly Progress Report based on a computer software system, which utilise critical path analysis and resource scheduling techniques.  The monthly report with cut off date of 10th shall be submitted to BPCL before 15th of the same month.  The report shall form the basis for discussion at the Monthly Progress Review Meeting. Minutes shall be prepared and submitted to BPCL for comment/approval no later than 48 hours after the meeting.

The monthly report shall include the following information as a minimum:

- Brief description of the significant accomplishments of the period, concerns, corrective actions and forthcoming activities for the next two months

- Brief discussion of current or anticipated unfavourable variances related to progress and resources

- Status of  Milestone Schedule

- Procurement status

- Overall Physical Progress 'S' Curve;

- ‘S’ curve for engineering, manufacturing & delivery, construction progress

- Financial report with ‘S’ curve and commitments Status Report.

OUTSOURCING :

Outsourcing at site shall be informed to BPCL sufficiently in advance from time to time. Corrective action by way of replacement shall be affected in case of impairment in performance. No key positions in each area of activity as per scope shall be outsourced.

D.  HSE GUIDELINES

1.	HSE Program

Program Requirements

CONSULTANT shall establish, operate and maintain for the term of the Contract an HSE Program.

CONSULTANT shall be responsible for the HSE Program development, implementation by contractors.

HSE Policy

CONSULTANT shall conduct its activities so as to:

*	Take foremost account of the health and safety of Consultant’s staff, all contractors staff and other persons who may be affected by its operations.

*	Protect the environment, prevent pollution and seek improvements in the efficient use of natural resources.

*	Ensure the safe installation and operation of all plant and equipment.

CONSULTANT shall pursue this policy through plans, training and any other means necessary to meet plan goals.  The guiding principles shall be as follows:

- HSE protection forms an integral part of the business plan.

- HSE protection is a line responsibility.

- All accidents are preventable.

HSE Objectives

CONSULTANT shall:

*	Encourage, support and pursue the continual improvement of health and safety at work and of the continual improvement of its environmental performance.

*	Support and promote a high standard of preventive and curative health care and the execution of effective occupational and public health programs.

*	Support and implement programs to promote and improve safe working methods and practices.

*	Ensure by design, quality assurance and auditing that facilities are built and maintained so as to meet approved standards for safe and healthy working, production and fire prevention.

*	Ensure the designs reduce emissions, effluents and wastes that are known to have a negative impact on the environment.

*	Provide continual improvement in energy efficiency and conservation of natural resources.

*	Ensure by prescribing procedures for preventive maintenance, inspection and auditing that equipment is installed, maintained and operated so as to minimise risk of injury to people, leakage, fire or other accident.

*	Ensure removal of facilities and/or equipment that will no longer be used and, as far is possible, restore the environment to it's original state.

*	Report and analyze any accident with follow up recommendations to prevent recurrence, with accountability for all lost time accidents at departmental level or above.

*	Promote awareness of skills in life saving, safety and environmental protection for staff and contractors staff.

*	Consider and evaluate contractors performance with regard to HSE when letting tenders.

Other Requirements

Provision shall be made for access by OWNER and/or their representatives, to the Consultant’s premises and to those of contractors, following award of the Contract, for the purposes of survCONSULTANTlance and/or audit.

2. 	HSE Plan

CONSULTANT shall prepare a plan for the management of all HSE aspects of the Project implementation, known as the "HSE Plan".  The HSE Plan shall be based on the requirements of the HSE management system.

The HSE Plan shall include an assessment of all identifiable HSE risks associated with the Project and shall indicate the proposed method of controlling those risks to an acceptable level. It shall also include measurable and realistic targets for HSE performance, covering, but not necessarily limited to:

*	Lost time injury frequency;

*	Number of statutory reportable events;

*	Injury severity data;

*	Predetermined targets for environmental emissions and waste production;

*	A follow-up system to ensure that all remedial actions required by OWNER and from the Consultant’s own reviews and investigations of accidents and incidents are closed out.

The HSE Plan shall include details of the proposed method of auditing the effectiveness of Consultant’s HSE management system as applied to the Project implementation.

The HSE Plan forms part of the Contract.  It shall be reviewed at least annually and updated as necessary to incorporate any proposed changes to the WORK and/or Contract.

2.1	Reporting

CONSULTANT shall submit a quarterly written HSE report to Owner’s Representative, covering the following matters as relevant:

*	Progress made against the HSE Plan;

*	An overview of all accidents and near-miss events;

*	Performance against HSE targets; total working hours for all personnel;

*	Details of the quantity and nature of any emissions and wastes generated;

*	Copies of all inspection reports, including those provided to external bodies;

*	A summary of the status of any remedial actions.

CONSULTANT shall submit an annual HSE report, which summarises Consultant’s performance and that of subcontractor(s) during the performance of the WORK in the preceding year. This report shall include the cumulative total number of accidents near misses and hours worked.

Notwithstanding the provision of a quarterly report, CONSULTANT shall follow the requirements of the OWNER accident and incident reporting and investigation procedure while on the OWNER site, installation or license.

3.	Compatibility of HSE Management Systems

Consultant’s HSE management system shall, where relevant, be compatible with OWNER HSE management system.  CONSULTANT shall liase with the OWNER representative to ensure that the roles and responsibilities in both systems are clearly defined and allocated and that they are clearly understood by all parties involved in the WORK.

Within the framework of its HSE management system, CONSULTANT shall work to HSE performance standards, which are compatible with those of Owner’s HSE management system.

The interfaces between CONSULTANT and OWNER shall be documented in the form of a Safety Management System Interface Document, which shall become part of the contract.

Where applicable, the Contract shall ensure that similar standards apply to the HSE management systems used by all Contract(s).

4. 	Health, Safety and Environmental Management System

CONSULTANT shall provide OWNER with a statement of its policy for health, safety and environmental (HSE) matters for review prior to the commencement of the WORK.  During the term of the Contract this policy shall not be revised or amended in respect to the WORK provided without prior notification to OWNER.

*	CONSULTANT shall perform the WORK under a formal system which follows the principles outlined in the Health and Safety Executive publication HS(G)65 "Successful Health and Safety Management", as may be revised from time to time.

*	Consultant’s HSE management system shall be adequately documented and shall be shown to be effective in implementing the aims and objectives of Consultant’s HSE policy.

Without prejudice to the foregoing, Consultant’s HSE management shall:

*	Incorporate measures which demonstrate that all personnel are competent to perform their tasks safely; and

*	Ensure that in the performance of the WORK, all hazards to the health of personnel, Work staff and third parties have been identified, assessed and eliminated where possible and are being controlled through formal planning methods and procedures.

4.1	Health and Occupational Safety

4.1.1	Objectives:

To obtain such information as will demonstrate the Consultant’s commitment to Owner’s high standards of safety, and to provide a safe working environment, which does not rely on Owner’s supervision for its success.

4.1.2	Considerations:

*	It is expected that a safety organisation and procedures are well established within the contractor's corporate organisation.  Application of these to the WORK needs to be considered to ensure maximum benefit is obtained.

4.1.3	Requirements:

CONSULTANT shall provide the following :

*	A copy of Consultant’s signed corporate safety policy.

*	A copy of Consultant’s corporate safety organisation indicating how the individual responsible for safety reports into the organisation.

*	Consultant’s accident statistics for the last 5 years, including those of Consultant’s Affiliates.

*	Description of any regular or special training programs implemented.

*	Outline of any initiatives taken or planned to promote health and safety.

4.2	Environmental Care

Objectives:

To obtain such information as will demonstrate the Consultant’s commitment to Owner’s high standards of environmental care.

Considerations:

Selecting materials and employing procedures that are not detrimental to the environment, need not incur greater cost provided they are addressed early in the design phase.  Rectification of environmental damage can incur greater costs than initial avoidance.

Requirements:

CONSULTANTs shall provide the following: a copy of Consultant’s environmental policy; an indication of those areas of where environmental issues will be assessed; an explanation of how environmental care will be managed.

5.	HSE Audits

CONSULTANTs and subcontractors shall be subject to audit in accordance with:

*	their approved HSE plan documents;

*	the Project documents referenced herein;

*	and/or any other Project document referenced in the Purchase Order/Contract;

*	the Purchase Order/contract documents;

*	Any codes/standards referenced in the Purchase order/ Contracts;

*	Any codes/standards referenced in their approved HSE plan documents.

#### E.  PROJECT QUALITY GUIDELINES

1.  	Quality System

System Requirements

CONSULTANT and all of its contractors and subcontractors shall establish, operate and maintain for the term of the Contract, quality systems in accordance with the latest revisions of the documents herein incorporated by reference;

Document Title                      		Document Number

Quality Systems- model for          	ISO 9001

Quality Assurance in Design,

Development, Production -

Installation, and Servicing.

Guidelines for Developing          	ISO 10013, draft

Quality Manuals.

Quality Management and Quality     	ISO 90045, draft

System Elements - Part 5:

Guidelines for Quality Plans

CONSULTANT shall be responsible for the quality system development, implementation and maintenance of all contractors and subcontractors.

2. 	Quality PLAN (QP)

CONSULTANT as well as its contractors and subcontractor(s) shall prepare a QP to be reviewed and approved by OWNER, that, as a minimum, described all activities, their control points, controlling document or procedure, CONSULTANT quality activity and the required result.  The format of the quality plan shall be as per Consultant’s standard form.  If the subcontractor's QP is not available, CONSULTANT shall expand it's own QP to include the activities of the subcontracted Work.  In either case, CONSULTANT shall indicate his intended inspection points at the subcontractor's site.

3. 	Quality Audits

CONSULTANT, all contractors, subcontractors and vendors shall be subject to audit in accordance with;

*	their approved quality system documents;

*	the Project documents referenced herein;

*	and/or any other Project document referenced in the Purchase Order/Contract;

*	the Purchase Order /Contract documents;

* 	any codes/standards referenced in the Purchase Order/ Contract;

*	any codes/standards referenced in their approved quality

## SECTION – III

PROJECT IMPLEMENTATION PHILOSOPHY

1.1	PRE-PROJECT WORKS:

Based on engineering work, the pre-project works of site development consisting of dismantling of existing facilities, site grading / levelling, internal roads, main drainage system, area lighting, communication system, etc. also  be awarded to contractors.

1.2	PROJECT MANAGEMENT ORGANIZATION

CONSULTANT to plan, initiate, guide, co-ordinate, supervise and control the entire Project implementation activities through a dedicated task force consisting of specialists and experts on various aspects of Project such as process design, engineering, contracts, purchase, inspection, construction, etc. The task force will be headed by a dynamic and competent Project Manager with proven ability in managing such large magnitude projects.

The task force  with name(s) of personnel would be proposed by the CONSULTANT, for review and acceptance by OWNER which shall be identified within 15 days of award of job

1.3 	All co-ordination and communications for the Project will be carried out under the overall guidance and control of Consultant’s Project Manager. Co-ordination and communication procedures will be developed by CONSULTANT soon after its appointment, in consultation with BPCL.

A documentation control cell will be formed for the Project which will operate under the supervision of the CONSULTANT. This cell will be responsible for all incoming and outgoing technical documents related to the project. These documents will be compiled as per agreed procedures, kept updated to latest revision and delivered to the designated agency(s).

1.4 	Management of Inputs is key to successful Project implementation. Consultant’s Project control and monitoring system will be based on management of inputs right at micro level. Computerised tracking system will be used to enable Consultant’s Project personnel to monitor timely availability of inputs at every stage from all agencies engaged in Project implementation.

1.5 	Mid-course changes are expensive and therefore, tendency for changes must be resisted, unless the selected design is unsafe, unworkable or uneconomical.

1.6 	Right approach for a Project plan is that it should be construction driven, since construction needs certain time, has to be performed in a certain sequence which is normally pre-determined and offers little flexibility when it comes to minimisation of time.

The construction plan is to be backed-up by a Procurement Plan and an Engineering Plan, which should offer maximum flexibility.

1.7 	It is proposed that CONSULTANT schedule the release of data sheets in such a way as to facilitate early ordering of long lead/critical equipment and bulk raw material for open art units, based on design work of CONSULTANT may be adopted. The decision regarding early placement of order shall be taken by OWNER depending on the merits.

1.8 	Emphasis would be placed on mechanising construction activities, modular concepts and prefabrication/ pre-cast methods as much as possible. Therefore the tenders/contracts should specify such requirement.

1.9 	CONSULTANT should use a good software package for material movement and contractors billing. Major/Sub-contractors should set up their PCs in the construction Office so that material movement and billing operation can be handled on PCs by the Contractors, CONSULTANT as well as BPCL.

1.10 	It is recommended that CONSULTANT establishes a suitable communication system at site, as approved by BPCL.  CONSULTANT and other major contractors are expected to transfer various documents electronically with proper back-up facility, this would enable their quicker transmission / availability.

SECTION-IV

### REMUNERATION, CONTRACT PRICE  AND PAYMENT TERMS

1.0     Preamble

1.1	Contract Price

OWNER shall compensate CONSULTANT, where specified, for full and complete performance of the WORK accepted by OWNER if CONSULTANT has complied with all the terms and conditions in all parts of the Contract.

  - Basis of Lump Sum Prices as set forth herein

BPCL propose consultant  to quote  lump-sum for complete project management consultancy as per the  scope of work for CCR project   including   utilities within battery limit from the mother header. Further consultant to quote separately for Utilities adequacy   study as detailed in . Annexure-2.

For utilities / offsite as detailed in Annexure-2 complete study to be carried out based on existing system in the Refinery, additional requirement on account of CCR.  Accordingly   charges to be quoted for  adequacy study of  utilities.

The fixed lump sum prices shall be inclusive of all costs, risk and expense, overhead, profit and/or total fee related to the satisfactory performance and completion of the WORK.  The  prices shall include any and all costs related to management, supervision, design, engineering, surveys, subcontracts, construction, attendance at all meetings with OWNER (whether at Owner’s premises, Owner’s nominated location or Consultant’s premises or any other location in India as applicable during Process/FEED/Conventional/ of the project), expediting, inspection, testing and quality assurance/quality control of the WORK, as more particularly described in the SCOPE OF WORK, or elsewhere in the CONTRACT.  Said lump sum prices   shall     include,      but   not   be limited  to, the costs of all labour (manpower costs of CONSULTANT), supervision, management, (including but not limited to wages, benefits, payroll, taxes, travel, accommodation expenses, and other costs thereto as are paid to employees), all equipment, rental  of     third    party    equipment,   communications equipment, communication charges , all administrative costs of Consultant’s operation, all reproduction and graphic costs of whatever kind, postage and courier expenses, all insurance requirements and coverage, and financing, and all other costs or expenses of any kind which directly or indirectly relate to accomplishing the WORK and complying in full with the provisions of the CONTRACT, and which are not otherwise set forth or referred to in the CONTRACT as a reimbursable expense.  All downtime (except as provided in the agreement) shall be to Consultant’s account and is deemed to be included in the fixed lump sum price, provided downtime results due to reasons attributable to CONSULTANT. The lump-sum price is however exclusive of all expenses on foreign travel and service tax which shall be payable at actual.

The Consultant’s   lump-sum   price is based on the agreed project Mechanical   completion   schedule and   completion  of  other Consultant’s  services against the contract viz. submission of recommendations for closing of contracts, as-built drawings, material reconciliation, Project Close out report and PG test run within six months of mechanical completion.

The  prices are further subject to and inclusive of the following :

Housing for Consultant’s personnel at Project site or elsewhere for fulfilment of project SERVICES shall be Consultant’s responsibility.

Adequate office space at project site (in the form of temporary building-at site with running water & electricity free of charge) will only be provided by the OWNER. Furniture and other communication facilities for Consultant’s own use are to be arranged by CONSULTANT.

Contract  labour for stores handling and any other purpose to be arranged by CONSULTANT.

- PRICE SCHEDULE:

2.1     LUMP SUM PRICE FOR PROJECT MANAGEMENT

CONSULTANCY AS PER THE SCOPE OF WORK .

For satisfactory performance and completion of the WORK by CONSULTANT, OWNER shall compensate CONSULTANT, lump sum prices for the  works   related to the NHT/CCR  Project.

Consultant shall   quote fixed lump sum fees for their  services as per the

above  scope  of work.

[To be filled in by Bidder]

Total Lump Sum Price - Rs. _____________ *(in figures)

(Rupees _____________________________________________ )(in words)

*   The Lump-sum price as above excludes all expenses on foreign travel and service tax  which shall be paid extra and payable at  actual.

- Consultant to furnish the total no. of man-months considered for the construction, commissioning works at site.

2.2   LUMP SUM PRICE  FOR   CARRYING OUT  UTILITIES          ADEQUACY STUDY FOR TOTAL UTILITIES REQUIREMENT FOR THE REFINERY POST NHT/CCR AS PER ANNEXURE-2 AND SUBMISSION OF ADEQUACY REPORT

For satisfactory performance and completion of the WORK by CONSULTANT, OWNER shall compensate CONSULTANT, lump sum prices for the works related to the Utilities of  NHT and CCR Units.

Consultant shall  quote fixed lump sum fees for their  services as per the

above  scope  of work.

[To be filled in by Bidder]

Total Lump Sum Price - Rs. _____________ *(in figures)

(Rupees _____________________________________________ )(in words)

*  The  price as above excludes all expenses on foreign travel and service tax  which shall be paid extra and payable at actual

2.3      Basis of Lump Sum Prices as set forth herein

The fixed lump sum prices shall be inclusive of all costs, risk and expense, overhead, profit and/or total fee related to the satisfactory performance and completion of the WORK.  The  prices shall include any and all costs related to management, supervision, design, engineering, surveys, subcontracts, construction, attendance at all meetings with OWNER (whether at Owner’s premises, Owner’s nominated location or Consultant’s premises or any other location in India as applicable during Process/execution of the project), expediting, inspection, testing and quality assurance/quality control of the WORK, as more particularly described in the SCOPE OF WORK, or elsewhere in the CONTRACT.  Said lump sum prices   shall     include,      but   not   be    limited  to, the costs of all labour (manpower costs of CONSULTANT), supervision, management, (including but not limited to wages, benefits, payroll, taxes, travel, accommodation expenses, and other costs thereto as are paid to employees), all equipment, rental  of     third    party    equipment,   communications equipment, communication charges , all administrative costs of Consultant’s operation (including home office and office space* for Owner’s representatives at Consultant’s offices), all reproduction and graphic costs of whatever kind, postage and courier expenses, all insurance requirements and coverage, and financing, and all other costs or expenses of any kind which directly or indirectly relate to accomplishing the WORK and complying in full with the provisions of the CONTRACT, and which are not otherwise set forth or referred to in the CONTRACT as a reimbursable expense.  All downtime (except as provided in the agreement) shall be to Consultant’s  account and is deemed to be included in the fixed lump sum price, provided downtime results due to reasons attributable to CONSULTANT. The lump-sum price is however exclusive of all expenses on foreign travel and service tax which shall be payable at actual.

The Consultant’s lump-sum price shall be based on the agreed project Mechanical completion schedule and completion of other Consultant’s  services against the contract viz. submission of recommendations for closing of contracts, as-built drawings, material reconciliation and PG test run within six months of mechanical completion.

The lump-sum prices shall be further subjected to and inclusive of the following :

a) Housing for Consultant’s personnel at Project site or elsewhere for

fulfilment of project SERVICES shall be Consultant’s responsibility.

b) Contract labour for stores handling and any other purpose.

c) Office space for Owner’s representative at Consultant’s office shall be

one cabin (about 100  sq.ft) with telephone line. However, STD/ISD

calls shall be paid by CONSULTANT on actual basis.

- PAYMENT SCHEDULE

3.1   FOR PROJECT MANAGEMENT CONSULTANCY AS PER SCOPE OF WORK OF CCR PROJECT

- Lump-sum Price

- 5% on completion of Kick-off Meeting, release of Project/Document Control Procedure, Co-ordination procedure, Activity Weighing basis & Draft Project Schedule.

- 5% on ordering of critical equipments viz. Reactors, plate type heat exchanger and HP compressors.

- 85% based on the project progress taken as an average of consultant’s progress and physical progress on monthly basis based on the mutually agreed milestones.

- 2% on commissioning.

- 1% on  order closing.

- 1%  on final documentation  and PG test

- 1% on completion of ware house activities including handing over of project surplus which is guaranteed within 5% of bulk material. CONSULTANT will assist liquidation of surplus material generated from conventional works under the contract.

- Any cost to be reimbursed by OWNER shall be paid on submission of invoices with supporting documents by CONSULTANT.

3.2    PAYMENT SCHEDULE- FOR UTILITIES STUDY AS IN ANNEXURE-2

AND SUBMISSION OF ADEQUACY REPORT

a)  Price

5% on completion of Kick-off Meeting,.

70% based on submission of draft report .

25 % on acceptance of report

- Any cost to be reimbursed by OWNER shall be paid on submission of invoices with supporting documents by CONSULTANT.

In  lieu of retention money, contractor shall submit bank guarantee of equivalent amount of retention money along with acknowledgement of purchase order valid for defects liability period of twelve months from the date of commissioning or eighteen months from the date of Mechanical completion, whichever is earlier. Bank guarantee shall have further claim period of 3 months beyond the end of defects liability period.

Service tax shall be paid on production of documentary proof of service tax regn. no. after verifying excise range details & service tax regn. no. in all invoices. Break up of basic cost for all items & service tax shall be provided in all invoices.

4.0	UNIT RATES

The unit rates set forth below shall be applied solely at Owner’s option for changes in the WORK and for resultant additions to or deletions from the fixed lump sum price(s) as set forth in paragraphs 2.0 of this   SECTION-IV.  Such adjustments to compensation to CONSULTANT shall be mutually agreed.

The unit rates are all inclusive as defined in paragraph 1.2 of this SECTION-IV. These rates are however exclusive of all expenses on travel but exclusive of service tax @10.3%.  In case of any increase or decrease of the service tax rate and/or imposition of such new tax/levy during the time of execution of job, service tax shall be paid at the prevailing rate at that time.

[To be filled in by Bidder]

| UNIT RATES |
| --- |
| 1. | MANHOUR RATES FOR HEAD OFFICE WORK (valid upto 31.3.2012) |  |
|  | Designation or equivalent | Rate (Rs.)/ Man hour |
| 2. | MANMONTH RATES FOR SITE WORK (valid upto 31.3.2012) |  |
|  | Designation or equivalent | Rate (Rs.)/ Man month |

Note :

- The man-hour rates are based on 8 hours per day/40 hour (5 days) per week normal working. The site man-month rates are based on 8 hours per day/48 hours (6 days) per week normal working. Additional hours shall be charged at the same rates.

- The Unit Rates shall be valid  till the commissioning of the project.

- Man month rates shall be applicable after completion of pre-commissioning activities and closing /handing over of warehouse after completion of reconciliation with contractor / disposal.

- No overstay compensation acceptable to BPCL. However similar rates are required for add on engineering at HO

### SECTION - V

### TIME  SCHEDULE

1.0	General

For PMC services, Project schedule shall be 26 months from the  date of handing over of critical equipment data sheets, which shall be considered as zero date for project schedule.

Bidder shall provide a Schedule of Work showing the dates / period for the Project Activities. The Schedule of Work shall be in the form of a bar chart schedule or schedules covering all aspects of the Work from award of Contract through to completion of commissioning of the Project considering the various activities detailed in Scope of Work.

Adequacy study for utilities including flare, Inst / process air system, hydrogen, nitrogen to be carried out  and  submit the report within 2  months from zero date based on process licensor data.

LD Clause - In case of delay 0.5% per week of delay or part thereof upto a max. 5% of the total contract value shall be recovered for both the above items independently.

2.0	Required Key Dates

Bidder shall identify and provide dates associated with completion of Milestones.

### SECTION -VI

WARRANTIES & GUARANTEES

1.1	General Warranties.  CONSULTANT warrants that:

1.1.1  	Personnel.  All professional personnel of CONSULTANT and its Subcontractors shall have proper qualifications for the Work assigned to them hereunder and shall deploy the required number of personnel. Premium for insurance policies as applicable except for the CONSULTANT personnel

1.1.2  	Standard of Care and Work.  CONSULTANT and each Subcontractor shall perform their obligations under this Contract in conformity with the highest international standards of care employed by leading engineering firms in the petroleum refining industry and all Work shall be first class.

1.1.3 	Management, Design and Development.  The management, design and development of the WORK shall conform with this Contract and shall be free of defects and deficiencies.  The management, design and development shall be such that the WORK shall comply with the terms of this Contract and shall meet all design, safety and performance and other criteria as specified herein.

1.1.4  	Work. The Work shall be fit for the purposes and uses intended and capable of use in the manner contemplated in the Contract.

1.1.5  	Other Services.  All Work performed by CONSULTANT and Subcontractors not otherwise mentioned in this Section 1.1, including, without limitation, inspections performed by CONSULTANT or its Subcontractors under this Contract, shall be adequate and sufficient for the purposes intended, in conformity with the terms of this Contract and free of defects and deficiencies.

Consultant’s obligation to manage, design and develop the Work correctly, and the General Warranties set forth above, shall not be reduced or affected by any inspection, test, acceptance or payment, Owner’s approval of any designs, drawings or specifications, or by the issue of the Certificate of Acceptance of the Work or any reperformance or replacement of any part of the Work.

1.2	Remediation.

1.2.1  	Notice.  At any time owner may by notice in writing to CONSULTANT, require CONSULTANT to remedy any defect in the Work by reperformance or replacement not later than 18 months from date of mechanical completion or 12 months from the date of commissioning, whichever is earlier.

    - Obligation to Remedy Breach.  CONSULTANT shall be obligated to effect, at its own expense, in the shortest practicable time, such reperformance and replacement as are necessary to remedy the breach as the result of such breach.

1.2.3  	Program for Reperformance and Replacements.  As soon as practicable, and in any event within 5 days after the receipt by CONSULTANT of Owner’s notice, CONSULTANT will submit for Owner’s approval a plan for effecting the reperformance or replacement required to remedy such breach.  If required by OWNER, CONSULTANT shall attend at the Site or at place(s) specified by the OWNER to inspect the defective Work and where appropriate carry out repairs to or replacement of the defective Work.

    - Owner’s Recourse.  If CONSULTANT does not begin its plan for reperformance and replacement within the time mutually agreed, or if CONSULTANT and OWNER fail to reach agreement on such a program within 5 days of the receipt by OWNER of Consultant’s plan submitted pursuant to Section 1.2.3, OWNER, after advising CONSULTANT in writing, shall be entitled at its option to perform or have third parties perform such work as is necessary to remedy or cause to be remedied.

1.2.5  	Other Rights and Remedies.  The rights and remedies of OWNER provided by this Section 1.2, are in addition to any other rights and remedies provided at law or in equity or otherwise.

1.3	Completion Warranty

1.3.1	Completion Warranty.  Without limiting the effect of the General Warranties or any other provision of this Contract, CONSULTANT warrants that mechanical completion of PROJECT shall occur no later than  26 months from the date of issue of LOI/TOI.

    - Effect of Breach.  Time is of the essence in the performance by CONSULTANT of its obligations under this Contract. If CONSULTANT breaches the special completion warranty set forth in Section 1.3.1 and the delay is attributable to CONSULTANT, CONSULTANT shall pay to OWNER as liquidated damages for delay (and not as a penalty) one-half percent (0.5%) of the Lump-sum Price for PMC Work ( Item-10) as of the date of execution of this Contract for each week of delay in mechanical completion up to a maximum aggregate amount in respect of such delay of five percent (5%) of the Lump-sum Price.  In addition, CONSULTANT shall be responsible for any and all additional costs necessary for completion of his scope of work.

CONSULTANT shall pay to OWNER as liquidated damages for delay (and not as a penalty) one-half percent (0.5%) of the Lump-sum Price for Adequacy check Report (Item-20) as of the date of execution of this Contract for each week of delay in mechanical completion up to a maximum aggregate amount in respect of such delay of five percent (5%) of the Lump-sum Price.  In addition, CONSULTANT shall be responsible for any and all additional costs necessary for completion of his scope of work.

1.4  Consequential Damages.  Neither party shall be responsible to the other for any penalty or consequential direct or indirect losses and damages such as loss of use of revenue, products or profits.

1.5  Limitation of liability. The overall limit of Consultant’s liability under this contract for all guarantees, warranties, liquidated damages of whatsoever nature, whether expressed or implied shall be limited to ten percent (10%) of the lump-sum price.

SECTION- VII

(OWNERS OBLIGATIONS)

  - To perform all functions falling within the scope of this CONTRACT as Owner’s responsibility till completion of PROJECT in accordance with agreed contract provisions.

  - In consultation with OWNER, CONSULTANT shall identify and allocate space inside the refinery premises for warehousing, storage of construction materials, contractor’s fabrication yard etc., for the unit/ facilities to be executed under this project. For additional space, the contractors shall be advised to look for space outside the refinery.

  - Site availability will be given progressively without affecting the site progress

  - Provide “As-built” drawings/ details to the extent available for existing units/ facilities.

  - Provide battery limit conditions (material balance) for existing units / facilities.

  - To act as Principal Employer and deal directly with local administration, labour laws, audit queries etc.

  - Interaction and liaison with all statutory authorities including Pollution Control Board, Excise, Custom, OISD, CEA/ Elect Inspector etc. CONSULTANT shall provide required technical documents for clearance by these bodies. Consultant’s representative shall accompany BPCL to provide technical assistance, if necessary.

  - Assume responsibility for handling of  insurance claim, disputes, extra claims of vendors / contractors till the last closing recommendation and compliance to warehouse management scope, assistance to handle the claims, disputes etc.  or 6 months after mechanical completion, whichever is earlier.

  - Arranging hot/ cold work permits for working in the existing areas.

  - To accord approvals within 2 weeks for all documents/ drawings falling under Owner’s approval category.

  - Progressively take over the facilities/units within two weeks of their mechanical Completion and pre-commissioning activities (unit-wise/system wise).

  - Provide requisite operating personnel during pre-commissioning/ commissioning/ guarantee performance test run of the new facilities/ units/ electric sub-station etc.

  - Provide watch and ward facilities at construction site.

  - To enter into contract agreement with Licensors/ Contractors/Vendors.

  - Handle litigation dispute, arbitration cases, if any. CONSULTANT will provide required technical assistance to OWNER.

  - Bear the cost of following :

- All material, equipments and consumable required & procured for construction, trial runs, pre-commissioning and commissioning :

- Transportation and handling charges for materials.

- All construction and erection costs.

.

- Third Party Inspection/ Testing charges for materials and equipments.

- Press advertisements costs for pre-qualification, tendering notifications, etc. for materials/ equipments and works/ contracts.

- Expenses towards security and safety of materials and equipments.

- All taxes, duties and statutory levies including Octroi charges, applicable for the project work.

- All charges for litigation, arbitration, disputes etc. with Licensor/vendor etc.

- Fees paid for various approvals, statutory clearances, etc.

- Provide adequate office accommodation for performance of SERVICES by CONSULTANT excluding furniture etc. for site office with running electricity and water free of charges.

SECTION - VIII

BIDDER’S ORGANISATION

1.0	General

Bidder shall provide details of the structure of its Project team (to work as a task force), the personnel for each function (process, mechanical, civil , instrument and electrical, etc.) and their experience.  The details should be of the team proposed for this Project.

The structure of the team could vary in terms of numbers/field of expertise/location of work for different phases of the Project Work.  Bidders are expected to provide complete details (called for herein) for all identified phases of the Work.

2.0	Organization Charts

An organization chart shall be provided of the overall Project structure.

Organization charts shall name personnel and show their line responsibility and reporting position.

10.0  COMMERCIAL TENDER TERMS AND CONDITIONS FOR PMC SERVICES FOR NAPHTHA HYDROTREATING AND CCR UNIT AT BPCL, MUMBAI REFINERY

BPCL TENDER NO. : BPCL( R) /P&CS /OT /11

10.0.1 GENERAL INSTRUCTIONS

- YOU ARE INVITED TO QUOTE IN TWO BIDS SYSTEM ( TECHNO-COMMERCIAL BID & PRICE BID ) FOR THE FOLLOWING ITEMS AS MENTIONED IN CONTAINT OF THIS TENDER.

- YOUR OFFER SHALL BE SENT TO THE ADDRESS MENTIONED IN THE PRESS TENDER NOTICE. YOU MAY ALSO PUT RUBBER STAMP OF YOUR ORGANIZATION ON THE ENVELOPE SO AS TO PARTLY COVER THE ADDRESS STICKER.

- YOUR OFFER CAN BE SENT BY COURIER / POST OR HAND DELIVERED. IN CASE OF HAND DELIVERY, TENDERS SHALL BE DEPOSITED IN P&CS TENDER BOX INSTALLED AT REFINERY MAIN GATE, MAHUL, BPCL REFINERY OR IN THE TENDER BOX INSTALLED AT P&CS DEPARTMENT AT SECOND FLOOR IN SOUTH BLOCK , ADMIN BUILDING OF REFINERY. TENDERS SHALL NOT BE HANDED OVER TO ANY PERSON OR DEPOSITED AT ANY OTHER PLACE.

- YOUR OFFER SHOULD REACH US ON OR BEFORE 10.00 AM ON THE DUE DATE.

- PLEASE MENTION YOUR UNIT VALUE BOTH IN WORDS AND FIGURES IN SCHEDULE OF RATES IN THE PRICE BID.

- YOUR QUOTED RATES OF SERVICES SHALL BE INCLUSIVE OF ALL APPLICABLE TAXES & DUTIES INCLUDING VAT, EXCEPT SERVICE TAX WHICH SHALL BE QUOTED SEPARATELY IF APPLICABLE. FORM-A (FOR SERVICE TAX) TO BE ATTACHED WITH THE PRICE BID. YOUR RATES SHALL REMAIN FIRM AS STATED IN THE TENDER. IN CASE THE BIDDER DOES NOT QUOTE FOR THE SERVICE TAX SEPARATELY, IT WILL BE ASSUMED THAT SERVICE TAX IS NOT APPLICABLE. NO CLAIM FOR THE SERVICE TAX WILL BE ENTERTAINED SUBSEQUENTLY

- KINDLY ENSURE TO STATE NAME AND DESIGNATION OF THE AUTHORITY SIGNING THE OFFER.

- PLEASE CONFIRM TO ALL OUR POINTS IN 'TERMS & CONDITIONS' OR ELSE WE WILL PRESUME THAT ALL OUR TERMS & CONDITIONS MENTIONED IN THIS TENDER ARE ACCEPTABLE TO YOU.

9)    NEFT PAYMENT:

Payments to contractors etc. shall be made by National Electronic Fund Transfer (NEFT) only. Payment by cheque will be made only to those vendors whose bank is located in the city where NEFT payment facility is presently not available. Bids received from vendors who are not accepting the NEFT payment terms are likely to be rejected.

Your quotation shall be forwarded in enclosed format only. Bids received in format other than the enclosed format are liable to be rejected.

10.1 BIDDING INSTRUCTIONS:

10.1.1 METHOD OF SUBMITTING CO TECHNO COMMERCIAL AND PRICED BIDS:

- YOUR QUOTATION SHOULD COMPRISE OF ONE COPY OF PRICE BID, TWO COPIES OF UNPRICED BID AND AN ENVELOPE OF EMD.

- ALL ABOVE MENTIONED FOUR SEALED ENVELOPES SHOULD BE SUPERSCRIBED WITH APPROPRIATE CAPTIONS. I.E. TENDER NO.  DATED , DUE ON , SUBJECT , TECHNO-COMMERCIAL ,PRICED, EMD ETC. AS THE CASE MAY BE.

- ABOVE FOUR ENVELOPES SHALL BE PUT IN COMMON SEALED ENVELOP MARKED WITH TENDER NO.  DATED , DUE ON , SUBJECT . ADDRESS OF RECEIVER AS PER NEWS PAPER ADVERTISE.

- THE PRICED AND UNPRICED BID SHALL BE IDENTICAL IN ALL ASPECTS EXCEPT THAT THE PRICED BID ALONE SHALL CONTAIN THE PRICE/S. ALL OTHER TERMS AND CONDITIONS APPEARING ON OUR INVITATION TO TENDER SHALL APPLY.

- NON COMPLIANCE SHALL RESULT IN REJECTION OF OFFERS.

6)   EARNEST MONEY DEPOSIT (EMD)

The bid must be accompanied by Earnest Money Deposit of Rs. 25 lakhs (Rs. Twenty Five Lakhs only ) in the form of crossed Demand Draft / Pay Order / Non-revocable Bank Guarantee in favour of Bharat Petroleum Corporation Limited, Mumbai. Bank Guarantee shall be on non-judicial stamp paper of value not less than Rs. 100 from any Scheduled Bank (other than Co-operative Bank) as per proforma enclosed. Validity of the Bank Guarantee shall be minimum 6 months from the Bid Due Date. EMD shall be submitted in separate sealed envelope in Techno-commercial Bid. Any bid not accompanied by Earnest Money Deposit (EMD) as stated above shall be rejected. Only Central Public Sector Enterprises are exempted from furnishing EMD subject to submission of declaration to that effect.

EMD will be forfeited if the bidder -

- Modifies / withdraws the offer during the validity period of 180 days

from the due date or extended due date of the tender.

- Does not produce acceptance of LOI or Purchase Order within 7

days time from the date of issue by the Owner

- Does not furnish the Security Deposit of required amount

- Is unable to make the facilities ready for operation within the

stipulated time after issuance of Letter of Intent regarding award of

contract and / or award of contract.

After acceptance of order by successful bidder, BPCL shall return the EMD to all unsuccessful bidders. EMD shall be returned to the successful bidder after he submits the security deposit to BPCL.

No interest shall be paid on Earnest Money Deposit.

10.2 CONTRACT RIDERS (CLAUSES):

10.2.1 TECHNO-COMMERCIAL BID WILL BE OPENED ON THE FOLLOWING

WORKING DAY ON DUE DATE.

10.2.2 ONE OF YOUR REPRESENTATIVE CAN WITNESS THE TECHNICAL BID OPENING OF YOUR OFFER ON THE FOLLOWING WORKING DAY ON  DUE DATE AT 2.00 PM AT P&CS CONFERENCE ROOM, 2ND FLOOR, SOUTH BOCK, ADMIN.BLDG. PLEASE LET US KNOW THE NAME OF THE PERSON WHO WILL BE ATTENDING THE SAME, TO ENABLE US TO PREPARE A WELCOME SLIP.

10.3 OTHER CONTRACTUAL STIPULATIONS:

10.3.1	THE BIDDER IS REQUESTED TO ADHERE TO TECHNICAL SPECIFICATIONS AS WELL AS COMMERCIAL TERMS.

DEVIATION : YOU ARE REQUESTED TO HAVE ALL YOUR QUERIES CLARIFIED BEFORE BIDDING. HOWEVER, IF YOU STILL HAVE DEVIATIONS FROM OUR RFQ AND THE ATTACHMENTS (SPECIFICATIONS / SCOPE OF WORK), PLEASE INDICATE DEVIATIONS IN YOUR OFFER UNDER A SEPARATE TITLE 'DEVIATIONS' GIVING REFERENCE TO RFQ CLAUSE NO. DEVIATIONS APPEARING UNDER CLAUSE 'DEVIATIONS' SHALL BE CONSIDERED WHILE EVALUATING THE OFFER. IN CASE YOUR OFFER DOES NOT CONTAIN A SEPARATE TITLE "DEVIATIONS", IT WILL BE CONSIDERED THAT YOU ARE ACCEPTING ALL THE CLAUSES AND SPECIFICATION IN TOTO.

10.3.2  	YOUR OFFER SHOULD BE VALID FOR A PERIOD OF 120 DAYS.

10.3.3	IF NOT BIDDING, PLEASE RETURN ENQUIRY DOCUMENTS ALONGWITH REGRET LETTER WITHIN DUE DATE.

10.3.4	BPCL RESERVES THE RIGHT TO GIVE PURCHASE PREFERENCE TO PUBLIC ENTERPRISES AS ADMISSIBLE UNDER EXISTING POLICY OF GOVT. OF INDIA.

10.3.5	OUR PAYMENT TERMS: PLEASE REFER BPCL TENDER SCOPE OF WORK ATTACHED HEREWITH.

10.3.6 	FOR FURTHER DETAILS/CLARIFICATION IF ANY, YOU MAY  PLEASE CONTACT OUR MANAGER P&CS ON PH. NO. 2553 3262.

10.3.7	ANY CHANGE TAXES & DUTIES DURING EXECUTION OF CONTRACT WILL BE CONSIDERED AGAINST ORIGINAL DOCUMENTARY PROOF.